## Control
Training and Observation Schedule
Package_ID | HB-RAMP-2026-07
Source_as_of | 2026-07-15
Approval_state | PENDING — no independent customer coverage authorized
Approval_deadline_UTC | 2026-07-17 17:00
Population | 10 representatives; all controlled states retained
Build_rule | Derived from supplied source records; do not manually patch output

## Controlled_Population
Rep_ID | Representative_Name | Segment | Territory_Code | Constraint_Type | Complete_Gates | Approved_Exception_Gates | Failed_Gates | Open_Gates | Blocked_Gates | Controlled_Status | Blocker_or_Next_Action | Next_Owner | Due_Date | Independent_Coverage_Authorized | Manager_Approval_State
REP-2701 | Maya Chen | Corporate | COR-W | None | 7 | 0 | 0 | 0 | 0 | Ready — manager approval pending | Evidence complete; independent coverage still requires desk manager approval | Desk Manager | 2026-07-17 17:00 | No | Pending desk manager review
REP-2702 | Jordan Patel | Affinity | AFF-E | Approved limited-coverage exception | 6 | 1 | 0 | 0 | 0 | Limited exception | GS-C07: Live observation moved to 2026-07-20; approved limited supervised low-risk coverage only | SUP-411 | 2026-07-20 | No | Pending desk manager review
REP-2703 | Sofia Ramirez | Education | EDU-MW | Contract terms remediation | 5 | 0 | 1 | 1 | 0 | Remediation | GS-C03: Contract terms retest scheduled 2026-07-17; GS-C07: Live observation blocked until contract retest passes | TRN-503 | 2026-07-17 | No | Pending desk manager review
REP-2704 | Ethan Brooks | Meetings | MTG-NE | State seller-of-travel licensing hold | 4 | 0 | 0 | 2 | 1 | Blocked | GS-C04: State seller-of-travel licensing hold blocks compliance signoff; GS-C06: Escalation scenario held until licensing release; GS-C07: No live observation until licensing release | COM-201 | 2026-07-22 | No | Pending desk manager review
REP-2705 | Priya Nair | Corporate | COR-NW | CRM audit remediation | 6 | 0 | 1 | 0 | 0 | Remediation | GS-C05: CRM audit missed deposit follow-up note; remediation scheduled | TRN-503 | 2026-07-16 | No | Pending desk manager review
REP-2706 | Liam O'Neill | Affinity | AFF-PA | Missed live observation slot | 6 | 0 | 0 | 1 | 0 | Pending evidence | GS-C07: Missed live observation due trainer calibration blackout | TRN-505 | 2026-07-17 | No | Pending desk manager review
REP-2707 | Ava Thompson | Education | EDU-S | None | 7 | 0 | 0 | 0 | 0 | Ready — manager approval pending | Evidence complete; independent coverage still requires desk manager approval | Desk Manager | 2026-07-17 17:00 | No | Pending desk manager review
REP-2708 | Noah Kim | Meetings | MTG-W | Compliance disclosure miss | 5 | 0 | 1 | 1 | 0 | Blocked | GS-C04: Critical disclosure miss on privacy wording; compliance retest required; GS-C07: Live observation held until compliance retest passes | COM-201 | 2026-07-18 | No | Pending desk manager review
REP-2709 | Isabella Reed | Corporate | COR-NE | Supervisor recommendation pending | 6 | 0 | 0 | 1 | 0 | Pending evidence | GS-C07: Supervisor recommendation panel scheduled 2026-07-17 | SUP-410 | 2026-07-17 | No | Pending desk manager review
REP-2710 | Marcus Lee | Affinity | AFF-N | Quote remediation cleared 2026-07-14 | 7 | 0 | 0 | 0 | 0 | Ready — manager approval pending | Evidence complete; independent coverage still requires desk manager approval | Desk Manager | 2026-07-17 17:00 | No | Pending desk manager review

## Cohort_Targets
Rep_ID | Representative_Name | Start_Date | Employment_Status | Prior_Travel_Sales_Experience | Location | Supervisor_ID | Supervisor_Name | Segment | Territory_Code | Constraint_Type | Target_Practice_Start | Target_Certification_Date | Target_Independent_Coverage_Date | Temporary_Coverage_Group | Account_Pool_Code
REP-2701 | Maya Chen | 2026-07-01 | Active | Corporate transient desk, 18 months | Chicago | SUP-410 | Alicia Benton | Corporate | COR-W | None | 2026-07-08 | 2026-07-18 | 2026-07-20 | West corporate overflow | POOL-COR-W
REP-2702 | Jordan Patel | 2026-07-01 | Active | Affinity member services, 2 years | Atlanta | SUP-411 | Marisol Grant | Affinity | AFF-E | Approved limited-coverage exception | 2026-07-08 | 2026-07-18 | 2026-07-20 | Affinity East renewal queue | POOL-AFF-E
REP-2703 | Sofia Ramirez | 2026-07-02 | Active | School travel coordinator, 8 months | Denver | SUP-412 | Nolan Price | Education | EDU-MW | Contract terms remediation | 2026-07-09 | 2026-07-19 | 2026-07-21 | Education Midwest queue | POOL-EDU-MW
REP-2704 | Ethan Brooks | 2026-07-02 | Active | Meetings inquiry desk, 1 year | Boston | SUP-413 | Dana Miller | Meetings | MTG-NE | State seller-of-travel licensing hold | 2026-07-09 | 2026-07-19 | 2026-07-22 | Meetings Northeast queue | POOL-MTG-NE
REP-2705 | Priya Nair | 2026-07-03 | Active | Leisure groups, 14 months | Seattle | SUP-410 | Alicia Benton | Corporate | COR-NW | CRM audit remediation | 2026-07-10 | 2026-07-20 | 2026-07-22 | Northwest corporate renewal queue | POOL-COR-NW
REP-2706 | Liam O'Neill | 2026-07-03 | Active | Member travel support, 10 months | Philadelphia | SUP-411 | Marisol Grant | Affinity | AFF-PA | Missed live observation slot | 2026-07-10 | 2026-07-20 | 2026-07-22 | Affinity Pennsylvania queue | POOL-AFF-PA
REP-2707 | Ava Thompson | 2026-07-01 | Active | Education account assistant, 2 years | Dallas | SUP-412 | Nolan Price | Education | EDU-S | None | 2026-07-08 | 2026-07-18 | 2026-07-20 | Education South queue | POOL-EDU-S
REP-2708 | Noah Kim | 2026-07-02 | Active | Event registration, 16 months | San Diego | SUP-413 | Dana Miller | Meetings | MTG-W | Compliance disclosure miss | 2026-07-09 | 2026-07-19 | 2026-07-22 | Meetings West queue | POOL-MTG-W
REP-2709 | Isabella Reed | 2026-07-01 | Active | Corporate agency desk, 3 years | New York | SUP-410 | Alicia Benton | Corporate | COR-NE | Supervisor recommendation pending | 2026-07-08 | 2026-07-18 | 2026-07-20 | Northeast corporate queue | POOL-COR-NE
REP-2710 | Marcus Lee | 2026-07-01 | Active | Affinity renewal sales, 2.5 years | Minneapolis | SUP-411 | Marisol Grant | Affinity | AFF-N | Quote remediation cleared 2026-07-14 | 2026-07-08 | 2026-07-18 | 2026-07-20 | Affinity North renewal queue | POOL-AFF-N

## Schedule
Event_ID | Rep_ID | Representative_Name | Controlled_Status | Event_Date | Start_Time | End_Time | Trainer_ID | Event_Type | Competency_ID | Prerequisite | Prerequisite_Check | Trainer_Qualification_Check | Availability_Window | Availability_Check | Blackout_Check | Window_Capacity | Trainer_Daily_Max | Scheduled_Slot_Number | Buffer_Rule | Buffer_Check | Event_State | Source_Basis | Independent_Coverage_Impact | Excluded_From_Execution | Exclusion_or_Delay_Reason | Action_Owner | Action_Due_Date | Next_Action
SCH-2701-MGR | REP-2701 | Maya Chen | Ready — manager approval pending |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | All GS-C01–GS-C07 evidence complete | PASS | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — MANAGER REVIEW | Evidence register; governance standard | None until signed desk manager approval | Yes | PENDING — MANAGER REVIEW; All GS-C01–GS-C07 evidence complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-20 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2707-MGR | REP-2707 | Ava Thompson | Ready — manager approval pending |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | All GS-C01–GS-C07 evidence complete | PASS | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — MANAGER REVIEW | Evidence register; governance standard | None until signed desk manager approval | Yes | PENDING — MANAGER REVIEW; All GS-C01–GS-C07 evidence complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-20 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2710-MGR | REP-2710 | Marcus Lee | Ready — manager approval pending |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | All GS-C01–GS-C07 evidence complete | PASS | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — MANAGER REVIEW | Evidence register; governance standard | None until signed desk manager approval | Yes | PENDING — MANAGER REVIEW; All GS-C01–GS-C07 evidence complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-20 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2705-RM | REP-2705 | Priya Nair | Remediation | 2026-07-16 | 8:30 | 9:30 | TRN-503 | Remaining remediation module: CRM hygiene rebuild | GS-C05 | GS-C01 complete | PASS | PASS — TRN-503 qualified for GS-C05 | 2026-07-16 08:30–12:30; capacity 3 | PASS | PASS | 3 | 3 | 1 | M501 → A-C05 >= 30 minutes | PASS — 30 minutes | SCHEDULED | EX-CRM-2705; Modules; Trainer_Roster; Availability_Windows | None until signed desk manager approval | No |  | TRN-503 | 2026-07-16 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2705-RT | REP-2705 | Priya Nair | Remediation | 2026-07-16 | 10:00 | 10:30 | TRN-503 | CRM audit retest | GS-C05 | CRM hygiene rebuild complete | CONDITIONAL — prior event must complete | PASS — TRN-503 qualified for GS-C05 | 2026-07-16 08:30–12:30; capacity 3 | PASS | PASS | 3 | 3 | 2 | M501 → A-C05 >= 30 minutes | PASS — 30 minutes | SCHEDULED — PREREQUISITE CONTROLLED | EX-CRM-2705; Assessments; Buffer_Rules | None until signed desk manager approval | No |  | TRN-503 | 2026-07-16 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2705-MGR | REP-2705 | Priya Nair | Remediation |  |  |  | DESK-MGR | Desk manager decision after retest | GS-C07 | GS-C05 retest passes; other gates complete | CONDITIONAL | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — RETEST AND MANAGER REVIEW | Evidence register; governance standard | None until signed desk manager approval | Yes | PENDING — RETEST AND MANAGER REVIEW; GS-C05 retest passes; other gates complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-22 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2703-RM | REP-2703 | Sofia Ramirez | Remediation | 2026-07-16 | 13:00 | 14:30 | TRN-503 | Remaining remediation module: contract terms | GS-C03 | GS-C02 complete | PASS | PASS — TRN-503 qualified for GS-C03 | 2026-07-16 13:00–16:30; capacity 3 | PASS | PASS | 3 | 3 | 1 | M301 → A-C03 >= 240 minutes | PASS — retest next day | SCHEDULED | EX-REM-2703; Modules; Trainer_Roster; Availability_Windows | None until signed desk manager approval | No |  | TRN-503 | 2026-07-16 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2703-RT | REP-2703 | Sofia Ramirez | Remediation | 2026-07-17 | 9:00 | 9:30 | TRN-503 | Contract assessment retest | GS-C03 | Contract terms remediation complete | CONDITIONAL — prior event must complete | PASS — TRN-503 qualified for GS-C03 | 2026-07-17 09:00–12:00; capacity 2 | PASS | PASS | 2 | 3 | 1 | M301 → A-C03 >= 240 minutes | PASS — 18.5 hours | SCHEDULED — PREREQUISITE CONTROLLED | EX-REM-2703; Assessments; Buffer_Rules | None until signed desk manager approval | No |  | TRN-503 | 2026-07-17 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2703-OBS | REP-2703 | Sofia Ramirez | Remediation | 2026-07-20 | 10:00 | 11:00 | TRN-505 | Live observation | GS-C07 | GS-C03 retest passes; GS-C02–GS-C06 complete | CONDITIONAL | PASS — TRN-505 qualified for GS-C07 | 2026-07-20 09:00–12:00; capacity 4 | PASS | PASS | 4 | 4 | 2 | No additional source buffer | PASS | TENTATIVE HOLD — PREREQUISITE CONTROLLED | Evidence GS-C07; Trainer_Roster; Availability_Windows | None until signed desk manager approval | Yes | TENTATIVE HOLD — PREREQUISITE CONTROLLED; Prerequisite: GS-C03 retest passes; GS-C02–GS-C06 complete | TRN-503 | 2026-07-21 | Complete M301 remediation and retest before live observation
SCH-2703-PNL | REP-2703 | Sofia Ramirez | Remediation |  |  |  | TRN-506 | Supervisor recommendation panel | GS-C07 | Live observation passes | CONDITIONAL | PASS — TRN-506 qualified for GS-C07 | No published TRN-506 window after 2026-07-20 observation | NO COMPLIANT WINDOW | N/A | 0 | 2 |  | A-C07 → supervisor recommendation >= 60 minutes | NOT TESTABLE | UNSCHEDULED — NEW WINDOW REQUIRED | Buffer_Rules; Availability_Windows | None until signed desk manager approval | Yes | UNSCHEDULED — NEW WINDOW REQUIRED; No published TRN-506 window after 2026-07-20 observation; Prerequisite: Live observation passes | TRN-506 (Dana Miller) | 2026-07-21 | TRN-506 must publish a post-observation panel slot and preserve the 60-minute observation-to-panel buffer.
SCH-2703-MGR | REP-2703 | Sofia Ramirez | Remediation |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | Retest, observation, and panel complete | CONDITIONAL | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — UPSTREAM EVENTS | Governance standard | None until signed desk manager approval | Yes | PENDING — UPSTREAM EVENTS; Retest, observation, and panel complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-21 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2706-OBS | REP-2706 | Liam O'Neill | Pending evidence | 2026-07-17 | 8:30 | 9:30 | TRN-505 | Live observation | GS-C07 | GS-C02–GS-C06 complete | PASS | PASS — TRN-505 qualified for GS-C07 | 2026-07-17 08:30–12:30; capacity 4 | PASS | PASS — before 13:00 blackout | 4 | 4 | 1 | A-C07 → supervisor recommendation >= 60 minutes | PASS — panel starts 60 minutes later | SCHEDULED | EX-LIVE-2706; Observations; Blackouts | None until signed desk manager approval | No |  | TRN-505 | 2026-07-17 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2706-PNL | REP-2706 | Liam O'Neill | Pending evidence | 2026-07-17 | 10:30 | 11:00 | TRN-506 | Supervisor recommendation panel | GS-C07 | Live observation passes | CONDITIONAL | PASS — TRN-506 qualified for GS-C07 | 2026-07-17 10:30–12:30; capacity 2 | PASS | PASS | 2 | 2 | 1 | A-C07 → supervisor recommendation >= 60 minutes | PASS — 60 minutes | SCHEDULED — PREREQUISITE CONTROLLED | EX-LIVE-2706; Buffer_Rules; Availability_Windows | None until signed desk manager approval | No |  | TRN-506 | 2026-07-17 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2706-MGR | REP-2706 | Liam O'Neill | Pending evidence |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | Observation and panel pass | CONDITIONAL | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — UPSTREAM EVENTS | Governance standard | None until signed desk manager approval | Yes | PENDING — UPSTREAM EVENTS; Observation and panel pass. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-22 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2709-PNL | REP-2709 | Isabella Reed | Pending evidence | 2026-07-17 | 10:30 | 11:00 | TRN-506 | Supervisor recommendation panel | GS-C07 | A-C07 evidence complete | PASS | PASS — TRN-506 qualified for GS-C07 | 2026-07-17 10:30–12:30; capacity 2 | PASS | PASS | 2 | 2 | 2 | A-C07 → supervisor recommendation >= 60 minutes | PASS — source evidence predates panel | SCHEDULED | EX-PANEL-2709; Trainer_Roster; Availability_Windows | None until signed desk manager approval | No |  | TRN-506 | 2026-07-17 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2709-MGR | REP-2709 | Isabella Reed | Pending evidence |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | Supervisor panel completes | CONDITIONAL | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — PANEL | Governance standard | None until signed desk manager approval | Yes | PENDING — PANEL; Supervisor panel completes. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-20 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2702-OBS | REP-2702 | Jordan Patel | Limited exception | 2026-07-20 | 9:00 | 10:00 | TRN-505 | Limited-exception live observation | GS-C07 | Low-risk supervised affinity renewals only | PASS — exception boundary active | PASS — TRN-505 qualified for GS-C07 | 2026-07-20 09:00–12:00; capacity 4 | PASS | PASS | 4 | 4 | 1 | A-C07 → supervisor recommendation >= 60 minutes | PENDING PANEL | SCHEDULED — LIMITED BOUNDARY | EX-LIM-2702; Availability_Windows | None until signed desk manager approval | No |  | TRN-505 | 2026-07-20 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2702-PNL | REP-2702 | Jordan Patel | Limited exception |  |  |  | TRN-506 | Supervisor recommendation panel | GS-C07 | Live observation passes | CONDITIONAL | PASS — TRN-506 qualified for GS-C07 | No published TRN-506 window after 2026-07-20 observation | NO COMPLIANT WINDOW | N/A | 0 | 2 |  | A-C07 → supervisor recommendation >= 60 minutes | NOT TESTABLE | UNSCHEDULED — NEW WINDOW REQUIRED | EX-LIM-2702; Buffer_Rules | None until signed desk manager approval | Yes | UNSCHEDULED — NEW WINDOW REQUIRED; No published TRN-506 window after 2026-07-20 observation; Prerequisite: Live observation passes | SUP-411 (Marisol Grant), coordinating TRN-506 | 2026-07-20 | SUP-411 must keep the limited boundary active and secure a TRN-506 panel slot at least 60 minutes after observation.
SCH-2702-MGR | REP-2702 | Jordan Patel | Limited exception |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | Observation and panel complete | CONDITIONAL | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | PENDING — LIMITED EXCEPTION REMAINS | Governance standard | None until signed desk manager approval | Yes | PENDING — LIMITED EXCEPTION REMAINS; Observation and panel complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-20 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2708-RM | REP-2708 | Noah Kim | Blocked | 2026-07-17 | 14:00 | 15:00 | TRN-504 | Remaining remediation module: compliance disclosure | GS-C04 | GS-C01 complete | PASS | PASS — TRN-504 qualified for GS-C04 | 2026-07-17 14:00–17:00; capacity 2 | PASS | PASS | 2 | 2 | 1 | M401 → A-C04 >= 120 minutes | RETEST EARLIEST 17:00 | SCHEDULED | EX-COMP-2708; Modules; Availability_Windows | None until signed desk manager approval | No |  | TRN-504 | 2026-07-17 | Complete the event only when its prerequisite check is satisfied; record resulting evidence before releasing downstream work.
SCH-2708-RT | REP-2708 | Noah Kim | Blocked |  |  |  | TRN-504 | Compliance retest | GS-C04 | Compliance remediation complete | CONDITIONAL | PASS — TRN-504 qualified for GS-C04 | Published window ends at earliest permitted retest start; TRN-504 blacked out 2026-07-20 | NO COMPLIANT WINDOW | PASS / 2026-07-20 BLACKOUT ENFORCED | 0 | 2 |  | M401 → A-C04 >= 120 minutes | FAIL — no duration remains at 17:00 | UNSCHEDULED — NEW WINDOW REQUIRED | EX-COMP-2708; Buffer_Rules; Blackouts | None until signed desk manager approval | Yes | UNSCHEDULED — NEW WINDOW REQUIRED; Published window ends at earliest permitted retest start; TRN-504 blacked out 2026-07-20; Prerequisite: Compliance remediation complete | COM-201, coordinating TRN-504 | 2026-07-18 | COM-201 must secure a new TRN-504 retest window beginning at least 120 minutes after coaching.
SCH-2708-OBS | REP-2708 | Noah Kim | Blocked | 2026-07-20 | 11:00 | 12:00 | TRN-505 | Live observation hold | GS-C07 | Compliance retest passes | BLOCKED | PASS — TRN-505 qualified for GS-C07 | 2026-07-20 09:00–12:00; capacity 4 | PASS | PASS | 4 | 4 | 3 | No additional source buffer | N/A | TENTATIVE HOLD — DO NOT EXECUTE UNTIL RETEST | Evidence GS-C07; Availability_Windows | None until signed desk manager approval | Yes | TENTATIVE HOLD — DO NOT EXECUTE UNTIL RETEST; Prerequisite: Compliance retest passes | COM-201, then TRN-505 after clearance | 2026-07-22 | COM-201 must record a passing compliance retest before TRN-505 may release the observation hold.
SCH-2708-PNL | REP-2708 | Noah Kim | Blocked |  |  |  | TRN-506 | Supervisor recommendation panel | GS-C07 | Compliance retest and live observation pass | BLOCKED | PASS — TRN-506 qualified for GS-C07 | No published window after conditional observation | NO COMPLIANT WINDOW | N/A | 0 | 2 |  | A-C07 → supervisor recommendation >= 60 minutes | NOT TESTABLE | UNSCHEDULED — UPSTREAM BLOCKER | Evidence register; Buffer_Rules | None until signed desk manager approval | Yes | UNSCHEDULED — UPSTREAM BLOCKER; No published window after conditional observation; Prerequisite: Compliance retest and live observation pass | COM-201, then TRN-506 after observation | 2026-07-22 | Clear compliance, complete the observation, then schedule TRN-506 at least 60 minutes later.
SCH-2708-MGR | REP-2708 | Noah Kim | Blocked |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | Compliance, observation, and panel complete | BLOCKED | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | BLOCKED — UPSTREAM EVENTS | Governance standard | None until signed desk manager approval | Yes | BLOCKED — UPSTREAM EVENTS; Compliance, observation, and panel complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-22 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.
SCH-2704-LIC | REP-2704 | Ethan Brooks | Blocked |  |  |  | COM-201 | Licensing clearance | GS-C04 | State seller-of-travel license confirmation | OPEN | N/A — compliance owner control | Due 2026-07-22; no owner availability supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | BLOCKED — COMPLIANCE OWNER ACTION | EX-LIC-2704 | None until signed desk manager approval | Yes | BLOCKED — COMPLIANCE OWNER ACTION; Due 2026-07-22; no owner availability supplied; Prerequisite: State seller-of-travel license confirmation | COM-201 | 2026-07-22 | COM-201 must confirm seller-of-travel license clearance in the evidence register.
SCH-2704-C04 | REP-2704 | Ethan Brooks | Blocked |  |  |  | TRN-504 | Compliance signoff / retest | GS-C04 | Licensing clearance | BLOCKED | PASS — TRN-504 qualified for GS-C04 | No published TRN-504 window after clearance due date | NO COMPLIANT WINDOW | 2026-07-20 blackout enforced | 0 | 2 |  | M401 → A-C04 >= 120 minutes if remediation assigned | NOT TESTABLE | UNSCHEDULED — LICENSE AND WINDOW REQUIRED | EX-LIC-2704; Availability_Windows; Blackouts | None until signed desk manager approval | Yes | UNSCHEDULED — LICENSE AND WINDOW REQUIRED; No published TRN-504 window after clearance due date; Prerequisite: Licensing clearance | COM-201, coordinating TRN-504 | 2026-07-22 | After license clearance, COM-201 must secure qualified TRN-504 capacity for compliance signoff or retest.
SCH-2704-C06 | REP-2704 | Ethan Brooks | Blocked |  |  |  | TRN-501 | Remaining escalation scenario | GS-C06 | GS-C03 and GS-C04 complete | BLOCKED | PASS — TRN-501 qualified for GS-C06 | No TRN-501 availability window supplied | NOT SUPPLIED | N/A | 0 | 4 |  | None | N/A | UNSCHEDULED — PREREQUISITE AND WINDOW REQUIRED | Evidence GS-C06; Trainer_Roster | None until signed desk manager approval | Yes | UNSCHEDULED — PREREQUISITE AND WINDOW REQUIRED; No TRN-501 availability window supplied; Prerequisite: GS-C03 and GS-C04 complete | COM-201, then TRN-501 after clearance | 2026-07-22 | After GS-C04 clears, COM-201 must secure a published TRN-501 window for the escalation scenario.
SCH-2704-OBS | REP-2704 | Ethan Brooks | Blocked |  |  |  | TRN-505 | Live observation | GS-C07 | GS-C02–GS-C06 complete | BLOCKED | PASS — TRN-505 qualified for GS-C07 | No published TRN-505 window after licensing due date | NO COMPLIANT WINDOW | N/A | 0 | 4 |  | A-C07 → supervisor recommendation >= 60 minutes | NOT TESTABLE | UNSCHEDULED — PREREQUISITES REQUIRED | Evidence GS-C07; Availability_Windows | None until signed desk manager approval | Yes | UNSCHEDULED — PREREQUISITES REQUIRED; No published TRN-505 window after licensing due date; Prerequisite: GS-C02–GS-C06 complete | COM-201, then TRN-505 after prerequisites | 2026-07-22 | After GS-C04 and GS-C06 clear, secure a qualified TRN-505 observation window.
SCH-2704-PNL | REP-2704 | Ethan Brooks | Blocked |  |  |  | TRN-506 | Supervisor recommendation panel | GS-C07 | Live observation passes | BLOCKED | PASS — TRN-506 qualified for GS-C07 | No compliant downstream window | NO COMPLIANT WINDOW | N/A | 0 | 2 |  | A-C07 → supervisor recommendation >= 60 minutes | NOT TESTABLE | UNSCHEDULED — UPSTREAM BLOCKER | Evidence register; Buffer_Rules | None until signed desk manager approval | Yes | UNSCHEDULED — UPSTREAM BLOCKER; No compliant downstream window; Prerequisite: Live observation passes | COM-201, then TRN-506 after observation | 2026-07-22 | After observation passes, secure TRN-506 capacity and enforce the 60-minute buffer.
SCH-2704-MGR | REP-2704 | Ethan Brooks | Blocked |  |  |  | DESK-MGR | Desk manager decision | GS-C07 | License, GS-C04, GS-C06, observation, and panel complete | BLOCKED | N/A — approval role | Desk manager availability not supplied | NOT SUPPLIED | N/A |  |  |  | None | N/A | BLOCKED — UPSTREAM EVENTS | Governance standard | None until signed desk manager approval | Yes | BLOCKED — UPSTREAM EVENTS; License, GS-C04, GS-C06, observation, and panel complete. Desk manager availability not supplied. | Rina Calder (Desk Manager) | 2026-07-22 | Complete any upstream events, submit the refreshed evidence package, and record the desk manager's signed decision.

## Modules
Module_ID | Module_Title | Duration_Minutes | Delivery_Mode | Prerequisite_Module_ID | Trainer_ID | Competency_ID
M101 | Discovery and segment fit | 120 | Workshop |  | TRN-501 | GS-C01
M201 | Negotiated air quote lab | 180 | Lab | M101 | TRN-502 | GS-C02
M301 | Group deposits and contract controls | 120 | Workshop | M201 | TRN-503 | GS-C03
M401 | Travel compliance disclosure clinic | 90 | Compliance clinic | M101 | TRN-504 | GS-C04
M501 | CRM opportunity hygiene practicum | 90 | CRM practicum | M101 | TRN-503 | GS-C05
M601 | Escalation and recovery scenarios | 120 | Simulation | M301; M401 | TRN-501 | GS-C06
M701 | Live group-call handoff lab | 180 | Live observation | M201; M301; M401; M501 | TRN-505 | GS-C07

## Competency_Map
Competency_ID | Competency_Name | Required_Evidence | Minimum_Rule | Prerequisite | Approval_Role
GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Intake complete | Trainer signoff
GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | GS-C01 | Product trainer signoff
GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | GS-C02 | Contract trainer signoff
GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | GS-C01 | Compliance signoff
GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | GS-C01 | QA signoff
GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | GS-C03 and GS-C04 | Supervisor recommendation
GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | GS-C02 through GS-C06 | Desk manager approval

## Assessments
Assessment_ID | Assessment_Name | Competency_ID | Minimum_Passing_Result | Measure_Type | Remediation_Module_ID
A-C01 | Discovery simulation | GS-C01 | 85 | Score | M101
A-C02 | Quote build practical | GS-C02 | 88 | Score | M201
A-C03 | Deposit and terms assessment | GS-C03 | 90 | Score | M301
A-C04 | Disclosure checklist | GS-C04 | 1 | Pass | M401
A-C05 | CRM audit | GS-C05 | 95 | Score | M501
A-C06 | Escalation scenario | GS-C06 | 85 | Score | M601
A-C07 | Live observation panel | GS-C07 | 90 | Score | M701

## Remediation_Options
Remediation_Module_ID | Remediation_Title | Competency_ID | Trainer_ID | Duration_Minutes
RM-C02 | Quote mechanics refresh | GS-C02 | TRN-502 | 75
RM-C03 | Contract terms remediation | GS-C03 | TRN-503 | 90
RM-C04 | Compliance disclosure retest prep | GS-C04 | TRN-504 | 60
RM-C05 | CRM hygiene rebuild | GS-C05 | TRN-503 | 60
RM-C07 | Live observation reschedule | GS-C07 | TRN-505 | 60

## Trainer_Roster
Trainer_ID | Trainer_Name | Trainer_Role | Qualified_Competency_IDs | Work_Location | Daily_Max_Observation_Slots
TRN-501 | Lena Ortiz | Enablement lead | GS-C01; GS-C06 | Chicago | 4
TRN-502 | Marco Vega | Air product trainer | GS-C02 | Remote | 3
TRN-503 | Helen Wu | Contract and CRM QA trainer | GS-C03; GS-C05 | Seattle | 3
TRN-504 | Omar Lewis | Compliance lead | GS-C04 | Atlanta | 2
TRN-505 | Erin Shah | Live observation coach | GS-C07 | Denver | 4
TRN-506 | Dana Miller | Supervisor panel lead | GS-C06; GS-C07 | Boston | 2

## Availability_Windows
Trainer_ID | Availability_Date | Start_Time | End_Time | Capacity_Slots | Window_Use
TRN-503 | 2026-07-16 | 8:30 | 12:30 | 3 | CRM and contract remediation
TRN-503 | 2026-07-16 | 13:00 | 16:30 | 3 | Contract remediation
TRN-503 | 2026-07-17 | 9:00 | 12:00 | 2 | Contract retest
TRN-504 | 2026-07-17 | 14:00 | 17:00 | 2 | Compliance retest
TRN-505 | 2026-07-17 | 8:30 | 12:30 | 4 | Live observation
TRN-505 | 2026-07-20 | 9:00 | 12:00 | 4 | Live observation
TRN-506 | 2026-07-17 | 10:30 | 12:30 | 2 | Supervisor recommendation panels
TRN-506 | 2026-07-18 | 13:00 | 15:00 | 2 | Supervisor recommendation panels

## Blackouts
Trainer_ID | Blackout_Date | Start_Time | End_Time | Blackout_Reason
TRN-505 | 2026-07-17 | 13:00 | 17:00 | QA calibration - no live observations
TRN-504 | 2026-07-20 | 8:00 | 17:00 | Privacy audit support
TRN-502 | 2026-07-16 | 13:00 | 17:00 | Peak quote desk coverage

## Buffer_Rules
From_Event | To_Event | Required_Buffer_Minutes | Rule_Note
M101 | A-C01 | 60 | Assessment after module
M301 | A-C03 | 240 | Terms remediation before retest
M401 | A-C04 | 120 | Disclosure coaching before retest
M501 | A-C05 | 30 | CRM rebuild before audit
A-C07 | Supervisor recommendation | 60 | Live observation to supervisor recommendation

## Validation
Check | Actual | Expected | Result
All ten reps retained in controlled population | 10 | 10 | PASS
All ten reps represented in remaining-event plan | 10 | 10 | PASS
Known exception owners represented | 7 | 7 | PASS
Scheduled events with unqualified trainer | 0 | 0 | PASS
Scheduled events violating blackout | 0 | 0 | PASS
Excluded/delayed rows with reason, owner, due date, and next action | 21 | 21 | PASS
Excluded/delayed rows missing a required control field | 0 | 0 | PASS
TRN-506 slots used on 2026-07-17 | 2 | 2 | PASS — at daily and window limit
TRN-505 slots held on 2026-07-20 | 3 | 4 | PASS — includes Noah conditional hold
Published-window conflict surfaced | 1 | 1 | PASS — Noah retest remains unscheduled
Independent coverage events | 0 | 0 | PASS

## Source_Lineage
Source_File | Bytes | SHA256
data/cohort_setup/july_new_rep_intake_targets.xlsx | 9915 | 01ace805f9015ae4fb04a6e92d1f034fdd3e5be1191c1a2b0fd4f83376d9de0f
data/cohort_setup/product_curriculum_and_competency_map.xlsx | 16436 | 7bfc8f3ad9235f24e996370f9a7c6b6c448a71de79e7028351c67d1dda8c327f
data/evidence_exports/certification_assessment_observation_export.xlsx | 28601 | b495110353576f72968e3503ea205c4a765d270189b77a2857595e89defd1542
data/availability/trainer_observation_availability.xlsx | 13287 | a26bb2adbc6a9c99dadc562261cd596492683f971080241f0bb0ff8850fbe1bd
data/account_coverage/temporary_group_account_coverage_export.xlsx | 20231 | e11e25ed4d864892b8f9584823fde8d9f9de3bbbcffc6696429078cbb3b641ed
data/governance/group_sales_ramp_certification_standard.docx | 325967 | cd2aaf69697175eb9e48dbb25a961b27d934a4a3ad37a74be9c90a83b18cfc7f
data/approvals/ramp_readiness_approval_request_thread.eml | 2363 | da88ab6219e96760410585350d3b69372384f7cf4673fe373cae9c831bd89f6f