## Manager Readiness Dashboard
Manager Readiness Dashboard
HB-RAMP-2026-07 ¦ approval request pending
Readiness_Status | Representatives
Ready - pending manager | 3
Limited exception - staged supervised | 1
Remediation required | 2
Pending evidence | 2
Blocked - unresolved exception | 2

## Definitions
Term | Definition
Ready - pending manager | All seven competencies evidenced; desk manager approval still pending
Limited exception - staged supervised | Approved limited exception exists; independent coverage still blocked
Remediation required | Failed evidence requires planned remediation or retest
Pending evidence | Evidence scheduled or not yet due
Blocked - unresolved exception | Licensing or compliance blocker unresolved

## Requirements
Competency_ID | Competency_Name | Required_Evidence | Minimum_Rule | Prerequisite | Approval_Role
GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Intake complete | Trainer signoff
GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | GS-C01 | Product trainer signoff
GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | GS-C02 | Contract trainer signoff
GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | GS-C01 | Compliance signoff
GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | GS-C01 | QA signoff
GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | GS-C03 and GS-C04 | Supervisor recommendation
GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | GS-C02 through GS-C06 | Desk manager approval

## Evidence Register
Rep_ID | Representative_Name | Competency_ID | Competency_Name | Required_Evidence | Minimum_Rule | Latest_Evidence | Evidence_Date | Score | Evidence_Status | Owner_ID | Due_Date | Exception_Code | Approval_State | Next_Action | Source_Reference
REP-2701 | Maya Chen | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C01
REP-2701 | Maya Chen | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C02
REP-2701 | Maya Chen | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C03
REP-2701 | Maya Chen | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C04
REP-2701 | Maya Chen | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C05
REP-2701 | Maya Chen | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C06
REP-2701 | Maya Chen | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Live observation and handoff note | 2026-07-12 | 95 | Complete | Desk |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2701-GS-C07
REP-2702 | Jordan Patel | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C01
REP-2702 | Jordan Patel | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C02
REP-2702 | Jordan Patel | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C03
REP-2702 | Jordan Patel | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C04
REP-2702 | Jordan Patel | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C05
REP-2702 | Jordan Patel | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2702-GS-C06
REP-2702 | Jordan Patel | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Limited exception memorandum | 2026-07-12 | 86 | Approved Exception | SUP-411 | 2026-07-20 | EX-LIM-2702 | Approved limited exception | Live observation moved to 2026-07-20; approved limited supervised low-risk coverage only | LMS-2702-GS-C07
REP-2703 | Sofia Ramirez | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2703-GS-C01
REP-2703 | Sofia Ramirez | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2703-GS-C02
REP-2703 | Sofia Ramirez | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 82 | Failed | TRN-503 | 2026-07-17 | EX-REM-2703 | Remediation scheduled | Contract terms retest scheduled 2026-07-17 | LMS-2703-GS-C03
REP-2703 | Sofia Ramirez | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2703-GS-C04
REP-2703 | Sofia Ramirez | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2703-GS-C05
REP-2703 | Sofia Ramirez | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2703-GS-C06
REP-2703 | Sofia Ramirez | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Not yet complete |  |  | Open | TRN-503 | 2026-07-17 | EX-REM-2703 | Remediation scheduled | Live observation blocked until contract retest passes | LMS-2703-GS-C07
REP-2704 | Ethan Brooks | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2704-GS-C01
REP-2704 | Ethan Brooks | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2704-GS-C02
REP-2704 | Ethan Brooks | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2704-GS-C03
REP-2704 | Ethan Brooks | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Not yet complete | 2026-07-14 |  | Blocked | COM-201 | 2026-07-22 | EX-LIC-2704 | Unresolved | State seller-of-travel licensing hold blocks compliance signoff | LMS-2704-GS-C04
REP-2704 | Ethan Brooks | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2704-GS-C05
REP-2704 | Ethan Brooks | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Not yet complete |  |  | Open | COM-201 | 2026-07-22 | EX-LIC-2704 | Unresolved | Escalation scenario held until licensing release | LMS-2704-GS-C06
REP-2704 | Ethan Brooks | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Not yet complete |  |  | Open | COM-201 | 2026-07-22 | EX-LIC-2704 | Unresolved | No live observation until licensing release | LMS-2704-GS-C07
REP-2705 | Priya Nair | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C01
REP-2705 | Priya Nair | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C02
REP-2705 | Priya Nair | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C03
REP-2705 | Priya Nair | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C04
REP-2705 | Priya Nair | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 91 | Failed | TRN-503 | 2026-07-16 | EX-CRM-2705 | Remediation scheduled | CRM audit missed deposit follow-up note; remediation scheduled | LMS-2705-GS-C05
REP-2705 | Priya Nair | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C06
REP-2705 | Priya Nair | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Live observation and handoff note | 2026-07-12 | 95 | Complete | Desk |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2705-GS-C07
REP-2706 | Liam O'Neill | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C01
REP-2706 | Liam O'Neill | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C02
REP-2706 | Liam O'Neill | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C03
REP-2706 | Liam O'Neill | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C04
REP-2706 | Liam O'Neill | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C05
REP-2706 | Liam O'Neill | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2706-GS-C06
REP-2706 | Liam O'Neill | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Not yet complete |  |  | Open | TRN-505 | 2026-07-17 | EX-LIVE-2706 | Pending evidence | Missed live observation due trainer calibration blackout | LMS-2706-GS-C07
REP-2707 | Ava Thompson | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C01
REP-2707 | Ava Thompson | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C02
REP-2707 | Ava Thompson | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C03
REP-2707 | Ava Thompson | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C04
REP-2707 | Ava Thompson | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C05
REP-2707 | Ava Thompson | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C06
REP-2707 | Ava Thompson | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Live observation and handoff note | 2026-07-12 | 95 | Complete | Desk |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2707-GS-C07
REP-2708 | Noah Kim | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2708-GS-C01
REP-2708 | Noah Kim | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2708-GS-C02
REP-2708 | Noah Kim | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2708-GS-C03
REP-2708 | Noah Kim | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 0 | Failed | COM-201 | 2026-07-18 | EX-COMP-2708 | Unresolved | Critical disclosure miss on privacy wording; compliance retest required | LMS-2708-GS-C04
REP-2708 | Noah Kim | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2708-GS-C05
REP-2708 | Noah Kim | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2708-GS-C06
REP-2708 | Noah Kim | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Not yet complete |  |  | Open | COM-201 | 2026-07-18 | EX-COMP-2708 | Unresolved | Live observation held until compliance retest passes | LMS-2708-GS-C07
REP-2709 | Isabella Reed | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C01
REP-2709 | Isabella Reed | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C02
REP-2709 | Isabella Reed | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C03
REP-2709 | Isabella Reed | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C04
REP-2709 | Isabella Reed | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C05
REP-2709 | Isabella Reed | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2709-GS-C06
REP-2709 | Isabella Reed | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Not yet complete |  |  | Open | SUP-410 | 2026-07-17 | EX-PANEL-2709 | Pending evidence | Supervisor recommendation panel scheduled 2026-07-17 | LMS-2709-GS-C07
REP-2710 | Marcus Lee | GS-C01 | Discovery and qualification | Discovery simulation pass | Score >= 85 | Discovery simulation pass | 2026-07-11 | 92 | Complete | Trainer |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C01
REP-2710 | Marcus Lee | GS-C02 | Group fare quote mechanics | Quote assessment pass | Score >= 88 | Quote assessment pass | 2026-07-12 | 94 | Complete | Product |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C02
REP-2710 | Marcus Lee | GS-C03 | Contract and deposit terms | Terms assessment pass | Score >= 90 | Terms assessment pass | 2026-07-13 | 93 | Complete | Contract |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C03
REP-2710 | Marcus Lee | GS-C04 | Compliance disclosures | Compliance checklist pass | Pass with no critical miss | Compliance checklist pass | 2026-07-14 | 2 | Complete | Compliance |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C04
REP-2710 | Marcus Lee | GS-C05 | CRM opportunity hygiene | CRM audit pass | Score >= 95 | CRM audit pass | 2026-07-10 | 99 | Complete | QA |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C05
REP-2710 | Marcus Lee | GS-C06 | Escalation judgment | Escalation scenario pass | Score >= 85 | Escalation scenario pass | 2026-07-11 | 90 | Complete | Supervisor |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C06
REP-2710 | Marcus Lee | GS-C07 | Customer handoff readiness | Live observation and handoff note | QA score >= 90 and supervisor signoff | Live observation and handoff note | 2026-07-12 | 95 | Complete | Desk |  |  | Evidence complete | Evidence meets July ramp standard | LMS-2710-GS-C07

## Exception View
Exception_Code | Rep_ID | Competency_ID | Exception_Reason | Approval_State | Exception_Opened_Date | Exception_Owner | Next_Action | Next_Action_Due_Date | Days_Open
EX-LIM-2702 | REP-2702 | GS-C07 | Approved limited exception | Approved limited exception | 2026-07-14 | SUP-411 | Keep Jordan on low-risk affinity renewals with senior rep review until live observation closes | 2026-07-20 | 3
EX-REM-2703 | REP-2703 | GS-C03 | Failed contract terms | Remediation scheduled | 2026-07-13 | TRN-503 | Complete M301 remediation and retest before live observation | 2026-07-17 | 4
EX-LIC-2704 | REP-2704 | GS-C04 | Licensing hold | Unresolved | 2026-07-11 | COM-201 | Compliance to confirm seller-of-travel license clearance | 2026-07-22 | 6
EX-CRM-2705 | REP-2705 | GS-C05 | CRM hygiene gap | Remediation scheduled | 2026-07-15 | TRN-503 | Rebuild CRM opportunity notes and pass audit | 2026-07-16 | 2
EX-LIVE-2706 | REP-2706 | GS-C07 | Missed live observation | Pending evidence | 2026-07-15 | TRN-505 | Complete live call observation before manager approval | 2026-07-17 | 2
EX-COMP-2708 | REP-2708 | GS-C04 | Compliance disclosure miss | Unresolved | 2026-07-14 | COM-201 | Pass disclosure retest and compliance review | 2026-07-18 | 3
EX-PANEL-2709 | REP-2709 | GS-C07 | Supervisor panel pending | Pending evidence | 2026-07-15 | SUP-410 | Complete supervisor recommendation panel | 2026-07-17 | 2

## Rep Readiness Summary
Rep_ID | Representative_Name | Segment | Supervisor_ID | Complete_Count | Required_Count | Approved_Exception_Count | Failed_Count | Open_or_Blocked_Count | Evidence_Complete_Pct | Readiness_Status | Approval_State
REP-2701 | Maya Chen | Corporate | SUP-410 | 7 | 7 | 0 | 0 | 0 | 100% | Ready - pending manager | HB-RAMP-2026-07 pending
REP-2702 | Jordan Patel | Affinity | SUP-411 | 6 | 7 | 1 | 0 | 0 | 85.71% | Limited exception - staged supervised | HB-RAMP-2026-07 pending
REP-2703 | Sofia Ramirez | Education | SUP-412 | 5 | 7 | 0 | 1 | 1 | 71.43% | Remediation required | HB-RAMP-2026-07 pending
REP-2704 | Ethan Brooks | Meetings | SUP-413 | 4 | 7 | 0 | 0 | 3 | 57.14% | Blocked - unresolved exception | HB-RAMP-2026-07 pending
REP-2705 | Priya Nair | Corporate | SUP-410 | 6 | 7 | 0 | 1 | 0 | 85.71% | Remediation required | HB-RAMP-2026-07 pending
REP-2706 | Liam O'Neill | Affinity | SUP-411 | 6 | 7 | 0 | 0 | 1 | 85.71% | Pending evidence | HB-RAMP-2026-07 pending
REP-2707 | Ava Thompson | Education | SUP-412 | 7 | 7 | 0 | 0 | 0 | 100% | Ready - pending manager | HB-RAMP-2026-07 pending
REP-2708 | Noah Kim | Meetings | SUP-413 | 5 | 7 | 0 | 1 | 1 | 71.43% | Blocked - unresolved exception | HB-RAMP-2026-07 pending
REP-2709 | Isabella Reed | Corporate | SUP-410 | 6 | 7 | 0 | 0 | 1 | 85.71% | Pending evidence | HB-RAMP-2026-07 pending
REP-2710 | Marcus Lee | Affinity | SUP-411 | 7 | 7 | 0 | 0 | 0 | 100% | Ready - pending manager | HB-RAMP-2026-07 pending

## Reconciliation Checks
Check | Formula_Result | Expected
Cohort reps | 10 | 10
Evidence rows | 70 | 70
Ready count | 3 | 3
Limited exception count | 1 | 1
Blocked count | 2 | 2

## Register Analysis
Competency | Open/failed evidence
GS-C01 | 0
GS-C02 | 0
GS-C03 | 1
GS-C04 | 2
GS-C05 | 1
GS-C06 | 1
GS-C07 | 5
Exception | Owner | Days open
EX-LIM-2702 | SUP-411 | 3
EX-REM-2703 | TRN-503 | 4
EX-LIC-2704 | COM-201 | 6
EX-CRM-2705 | TRN-503 | 2
EX-LIVE-2706 | TRN-505 | 2
EX-COMP-2708 | COM-201 | 3
EX-PANEL-2709 | SUP-410 | 2
Rep | Complete evidence %
REP-2701 | 100%
REP-2702 | 85.71%
REP-2703 | 71.43%
REP-2704 | 57.14%
REP-2705 | 85.71%
REP-2706 | 85.71%
REP-2707 | 100%
REP-2708 | 71.43%
REP-2709 | 85.71%
REP-2710 | 100%