APPROVAL-READY WORKING PACKAGE

# Group Sales Ramp Readiness Playbook

July 2026 cohort | HB-RAMP-2026-07 pending desk manager review

This playbook is staged for review. It does not approve independent customer coverage for any representative.

| Package Field | Package Value |
| --- | --- |
| Owner | Alicia Benton, frontline group-sales supervisor |
| Approval request | HB-RAMP-2026-07 |
| Source refresh | Evidence and account exports through 2026-07-15 |
| Decision state | Approval-ready request; desk manager decision pending |

# Contents

# Operating Scope

The playbook governs the July cohort before independent customer coverage. It carries ready, limited-exception, remediation, pending-evidence, and blocked representatives in one control population so the desk can stage actions without executing them prematurely.

# Entry Criteria and Decision Logic

| Readiness Status | Condition | Coverage Rule |
| --- | --- | --- |
| Ready - pending manager | All seven competencies complete | Stage handoff, do not execute |
| Limited exception - staged supervised | Approved exception but GS-C07 remains open | Low-risk supervised affinity only |
| Remediation required | Failed assessment or audit | Temporary owner retains account |
| Pending evidence | Observation or panel scheduled | Temporary owner retains account |
| Blocked - unresolved exception | Licensing or compliance hold | Supervisor escalation only |

# RACI and Handoff Ownership

| Work | Trainer | Supervisor | Desk Manager | Compliance | Coverage Owner |
| --- | --- | --- | --- | --- | --- |
| Close scheduled evidence gaps | R | A | I | C | I |
| Maintain exception owners and due dates | C | R/A | I | R for compliance | I |
| Stage account handoffs | I | R | A pending | C | R |
| Approve independent coverage | I | R | A | C | C |

# Readiness Process Flow

Figure 1 summarizes the handoff path used for this pending package.

Readiness Evidence Gate and Handoff Flow

July cohort actions stay staged until desk manager approval

| Swimlane | Native Process Path | Decision Owner | Exception Branch | Coverage Rule |
| --- | --- | --- | --- | --- |
| Ready path | Intake -> scheduled curriculum -> supervised practice -> GS-C01 through GS-C07 complete | Supervisor recommends readiness; desk manager decision remains pending | No exception branch needed | Eligible handoff is staged only after approval |
| Remediation | Register shows failed assessment, CRM gap, or open panel evidence | Trainer or supervisor owns next action and due date | Remediation or retest returns to evidence gate | Temporary owner retains customer action |
| Limited exception | REP-2702 has approved limited exception while GS-C07 live observation remains open | Supervisor keeps senior review through 2026-07-20 observation | Approved exception permits supervised low-risk affinity coverage only | No independent coverage |
| Blocked | Licensing or compliance hold blocks readiness | Compliance owner clears blocker before recommendation | Blocked path remains unresolved until clearance | Supervisor escalation only |

Figure 1. Readiness evidence gate, exception, and temporary coverage flow for HB-RAMP-2026-07.

Source: ramp standard, certification evidence register, schedule exceptions, and pending approval thread.

| Lane | Evidence Gate | Decision Branch | Coverage Action | Approval State |
| --- | --- | --- | --- | --- |
| Ready | GS-C01 through GS-C07 complete | Supervisor recommends readiness | Eligible handoff staged after manager approval | Pending |
| Limited | Approved exception exists | Only limited supervised path allowed | Low-risk affinity coverage with senior review | Approved exception, not independent approval |
| Remediation | Failed assessment or CRM audit | Schedule module or retest | Temporary owner keeps customer action | Pending evidence |
| Blocked | Licensing or compliance unresolved | Compliance owner clears blocker | Supervisor escalation for accounts | Unresolved |

Table 4. Editable lane detail for the readiness process-flow diagram.

# Representative Ramp Plan Appendix

| Rep ID | Representative | Segment | Target Cert | Readiness | Next Action |
| --- | --- | --- | --- | --- | --- |
| REP-2701 | Maya Chen | Corporate | 2026-07-18 | Ready - pending manager | Submit as ready pending manager review |
| REP-2702 | Jordan Patel | Affinity | 2026-07-18 | Limited exception - staged supervised | Approved limited-coverage exception |
| REP-2703 | Sofia Ramirez | Education | 2026-07-19 | Remediation required | Contract terms remediation |
| REP-2704 | Ethan Brooks | Meetings | 2026-07-19 | Blocked - unresolved exception | State seller-of-travel licensing hold |
| REP-2705 | Priya Nair | Corporate | 2026-07-20 | Remediation required | CRM audit remediation |
| REP-2706 | Liam O'Neill | Affinity | 2026-07-20 | Pending evidence | Missed live observation slot |
| REP-2707 | Ava Thompson | Education | 2026-07-18 | Ready - pending manager | Submit as ready pending manager review |
| REP-2708 | Noah Kim | Meetings | 2026-07-19 | Blocked - unresolved exception | Compliance disclosure miss |
| REP-2709 | Isabella Reed | Corporate | 2026-07-18 | Pending evidence | Supervisor recommendation pending |
| REP-2710 | Marcus Lee | Affinity | 2026-07-18 | Ready - pending manager | Quote remediation cleared 2026-07-14 |

# Exception Escalation Paths

| Exception | Rep ID | Reason | State | Owner | Due | Next Action |
| --- | --- | --- | --- | --- | --- | --- |
| EX-LIM-2702 | REP-2702 | Approved limited exception | Approved limited exception | SUP-411 | 2026-07-20 | Keep Jordan on low-risk affinity renewals with senior rep review until live observation closes |
| EX-REM-2703 | REP-2703 | Failed contract terms | Remediation scheduled | TRN-503 | 2026-07-17 | Complete M301 remediation and retest before live observation |
| EX-LIC-2704 | REP-2704 | Licensing hold | Unresolved | COM-201 | 2026-07-22 | Compliance to confirm seller-of-travel license clearance |
| EX-CRM-2705 | REP-2705 | CRM hygiene gap | Remediation scheduled | TRN-503 | 2026-07-16 | Rebuild CRM opportunity notes and pass audit |
| EX-LIVE-2706 | REP-2706 | Missed live observation | Pending evidence | TRN-505 | 2026-07-17 | Complete live call observation before manager approval |
| EX-COMP-2708 | REP-2708 | Compliance disclosure miss | Unresolved | COM-201 | 2026-07-18 | Pass disclosure retest and compliance review |
| EX-PANEL-2709 | REP-2709 | Supervisor panel pending | Pending evidence | SUP-410 | 2026-07-17 | Complete supervisor recommendation panel |

# Staged Handoff Checklist

| Checklist Field | Required Evidence | Owner |
| --- | --- | --- |
| Readiness status reconciled | Register readiness summary and evidence rows agree | Supervisor |
| Schedule gaps closed or owned | Schedule exceptions carry due date and owner | Trainer or supervisor |
| Account coverage disposition set | Each of 16 accounts has one staged allocation status | Coverage owner |
| Manager decision requested | Package submitted without external customer commitment | Desk manager |