## Schedule Dashboard
Schedule Dashboard
HB-RAMP-2026-07 ¦ pending desk manager approval
Session_Date | Remediation | Retest | Observation/panel
2026-07-16 | 2 | 1 | 0
2026-07-17 | 0 | 2 | 2
2026-07-18 | 0 | 0 | 1
2026-07-20 | 0 | 0 | 1
Trainer_ID | Booked slots | Available slots
TRN-503 | 10 | 8
TRN-504 | 1 | 2
TRN-505 | 2 | 8
TRN-506 | 2 | 4

## Parameters
Parameter | Value | Note
Approval_Request_ID | HB-RAMP-2026-07 | Manager review remains pending
Workday_Start | 8:30 | Earliest scheduled start
Workday_End | 17:00 | Latest scheduled end
Default_Buffer_Minutes | 1416:00 | Minimum between observation and recommendation

## Source_Cohort
Rep_ID | Representative_Name | Segment | Supervisor_ID | Target_Certification_Date | Target_Independent_Coverage_Date | Constraint_Type
REP-2701 | Maya Chen | Corporate | SUP-410 | 2026-07-18 | 2026-07-20 | None
REP-2702 | Jordan Patel | Affinity | SUP-411 | 2026-07-18 | 2026-07-20 | Approved limited-coverage exception
REP-2703 | Sofia Ramirez | Education | SUP-412 | 2026-07-19 | 2026-07-21 | Contract terms remediation
REP-2704 | Ethan Brooks | Meetings | SUP-413 | 2026-07-19 | 2026-07-22 | State seller-of-travel licensing hold
REP-2705 | Priya Nair | Corporate | SUP-410 | 2026-07-20 | 2026-07-22 | CRM audit remediation
REP-2706 | Liam O'Neill | Affinity | SUP-411 | 2026-07-20 | 2026-07-22 | Missed live observation slot
REP-2707 | Ava Thompson | Education | SUP-412 | 2026-07-18 | 2026-07-20 | None
REP-2708 | Noah Kim | Meetings | SUP-413 | 2026-07-19 | 2026-07-22 | Compliance disclosure miss
REP-2709 | Isabella Reed | Corporate | SUP-410 | 2026-07-18 | 2026-07-20 | Supervisor recommendation pending
REP-2710 | Marcus Lee | Affinity | SUP-411 | 2026-07-18 | 2026-07-20 | Quote remediation cleared 2026-07-14

## Availability
Trainer_ID | Availability_Date | Start_Time | End_Time | Capacity_Slots | Window_Use
TRN-503 | 2026-07-16 | 8:30 | 12:30 | 3 | CRM and contract remediation
TRN-503 | 2026-07-16 | 13:00 | 16:30 | 3 | Contract remediation
TRN-503 | 2026-07-17 | 9:00 | 12:00 | 2 | Contract retest
TRN-504 | 2026-07-17 | 14:00 | 17:00 | 2 | Compliance retest
TRN-505 | 2026-07-17 | 8:30 | 12:30 | 4 | Live observation
TRN-505 | 2026-07-20 | 9:00 | 12:00 | 4 | Live observation
TRN-506 | 2026-07-17 | 10:30 | 12:30 | 2 | Supervisor recommendation panels
TRN-506 | 2026-07-18 | 13:00 | 15:00 | 2 | Supervisor recommendation panels

## Evidence_Gaps
Rep_ID | Competency_ID | Gap_Type | Priority | Reason | Owner_ID | Due_Date
REP-2702 | GS-C07 | Live observation pending | Medium | Approved limited exception closes after 2026-07-20 observation | TRN-505 | 2026-07-20
REP-2703 | GS-C03 | Failed contract assessment | High | Retest before live observation | TRN-503 | 2026-07-17
REP-2704 | GS-C04 | Licensing hold | Blocked | No schedule until compliance releases hold | COM-201 | 2026-07-22
REP-2705 | GS-C05 | CRM audit failed | High | CRM remediation and audit required | TRN-503 | 2026-07-16
REP-2706 | GS-C07 | Live observation missed | Medium | Rescheduled before trainer blackout | TRN-505 | 2026-07-17
REP-2708 | GS-C04 | Compliance disclosure miss | High | Retest required before observation | TRN-504 | 2026-07-18
REP-2709 | GS-C07 | Supervisor recommendation pending | Medium | Panel scheduled | SUP-410 | 2026-07-17

## Scheduled Sessions
Session_ID | Rep_ID | Module_ID | Competency_ID | Session_Type | Trainer_ID | Session_Date | Start_Time | End_Time | Duration_Min | Prerequisite_Status | Capacity_Slots | Booked_Same_Trainer_Date | Buffer_Min | Conflict_Flag | Schedule_Status | Confirmation_State | Session_Note
SES-0716-01 | REP-2705 | M501 | GS-C05 | CRM remediation | TRN-503 | 2026-07-16 | 9:00 | 10:30 | 90 | Met | 6 | 3 | 30 | Clear | Confirmed | Confirmed | Rebuild CRM notes before audit
SES-0716-02 | REP-2705 | A-C05 | GS-C05 | CRM retest | TRN-503 | 2026-07-16 | 11:00 | 11:45 | 45 | Met | 6 | 3 | 30 | Clear | Confirmed | Confirmed | QA audit after remediation
SES-0716-03 | REP-2703 | M301 | GS-C03 | Contract remediation | TRN-503 | 2026-07-16 | 13:00 | 15:00 | 120 | Met | 6 | 3 | 240 | Clear | Confirmed | Confirmed | Terms remediation before retest
SES-0717-01 | REP-2703 | A-C03 | GS-C03 | Contract retest | TRN-503 | 2026-07-17 | 10:00 | 11:00 | 60 | Met | 2 | 1 | 60 | Clear | Proposed | Proposed | Must pass before live observation
SES-0717-02 | REP-2706 | M701 | GS-C07 | Live observation | TRN-505 | 2026-07-17 | 9:00 | 10:00 | 60 | Met | 4 | 1 | 60 | Clear | Confirmed | Confirmed | Rescheduled before Erin blackout
SES-0717-03 | REP-2709 | A-C07 | GS-C07 | Supervisor panel | TRN-506 | 2026-07-17 | 11:00 | 12:00 | 60 | Met | 2 | 1 | 60 | Clear | Confirmed | Confirmed | Recommendation panel
SES-0717-04 | REP-2708 | A-C04 | GS-C04 | Compliance retest | TRN-504 | 2026-07-17 | 15:00 | 16:00 | 60 | Met | 2 | 1 | 120 | Clear | Proposed | Proposed | Retest before any live observation
SES-0718-01 | REP-2705 | A-C07 | GS-C07 | Supervisor panel | TRN-506 | 2026-07-18 | 13:00 | 14:00 | 60 | Met | 2 | 1 | 60 | Clear | Proposed | Proposed | Manager recommendation after CRM retest
SES-0720-01 | REP-2702 | M701 | GS-C07 | Live observation | TRN-505 | 2026-07-20 | 10:00 | 11:00 | 60 | Met | 4 | 1 | 60 | Clear | Proposed | Proposed | Close approved limited exception

## Representative View
Rep_ID | Representative_Name | Segment | Target_Certification_Date | Open_Gaps | Scheduled_Items | Schedule_Status | Readiness_Status | Constraint_Type
REP-2701 | Maya Chen | Corporate | 2026-07-18 | 0 | 0 | No open gap | Ready - pending manager | None
REP-2702 | Jordan Patel | Affinity | 2026-07-18 | 1 | 1 | Scheduled | Limited exception - staged supervised | Approved limited-coverage exception
REP-2703 | Sofia Ramirez | Education | 2026-07-19 | 1 | 2 | Scheduled | Remediation required | Contract terms remediation
REP-2704 | Ethan Brooks | Meetings | 2026-07-19 | 1 | 0 | Unscheduled | Blocked - unresolved exception | State seller-of-travel licensing hold
REP-2705 | Priya Nair | Corporate | 2026-07-20 | 1 | 3 | Scheduled | Remediation required | CRM audit remediation
REP-2706 | Liam O'Neill | Affinity | 2026-07-20 | 1 | 1 | Scheduled | Pending evidence | Missed live observation slot
REP-2707 | Ava Thompson | Education | 2026-07-18 | 0 | 0 | No open gap | Ready - pending manager | None
REP-2708 | Noah Kim | Meetings | 2026-07-19 | 1 | 1 | Scheduled | Blocked - unresolved exception | Compliance disclosure miss
REP-2709 | Isabella Reed | Corporate | 2026-07-18 | 1 | 1 | Scheduled | Pending evidence | Supervisor recommendation pending
REP-2710 | Marcus Lee | Affinity | 2026-07-18 | 0 | 0 | No open gap | Ready - pending manager | Quote remediation cleared 2026-07-14

## Schedule Exceptions
Rep_ID | Exception_State | Reason | Owner_ID | Due_Date | Exception_Type
REP-2704 | Not scheduled | Licensing hold blocks compliance and observation | COM-201 | 2026-07-22 | Blocked
REP-2703 | Observation held | Live observation waits for contract retest result | TRN-503 | 2026-07-17 | Dependency
REP-2708 | Observation held | Compliance disclosure retest must pass first | TRN-504 | 2026-07-18 | Dependency

## Schedule Feasibility
Stage_Status | Representatives
Ready or manager pending | 3
Limited exception | 1
Remediation | 2
Pending evidence | 2
Blocked | 2
Segment | High-risk reps
Corporate | 2
Affinity | 2
Education | 1
Meetings | 2

## Formula Checks
Check | Formula_Result | Expected
Scheduled sessions | 9 | 9
Conflict flags not clear | 0 | 0
Unscheduled blocked reps | 1 | 1