## Workability Board
Northstar Sprint Workability Board
The control decision comes before risk priority: approved desk work, customer release, controlled exceptions, and holds are separate lanes.
Control Lane | Current Count | Account IDs | Can the Desk Work It Now? | Can the Rep Contact the Customer Now? | Release Rule | Owner | Control Note
WORK NOW — CLEAR / PREPARE | 12 | A-1001, A-1002, A-1003, A-1004, A-1005, A-1006, A-1007, A-1008, A-1009, A-1010, A-1011, A-1012 | Yes — supervisor and owner rep may complete the named evidence and prepare the approved action. | No accounts are customer-ready in the supplied evidence snapshot. | Customer contact only after all four row-level source controls calculate a Cleared release. | Dana Morales | These accounts are approved for local execution; rank applies only inside this lane.
CUSTOMER-READY NOW |  | See Cleared Contact Path | Only accounts displayed on Cleared Contact Path are released for dated contact. | Only after Release Status calculates Cleared | Current case exports show an open dependency, missing confirmation, or required deliverable for every approved row at package creation. | Dana Morales | Reassess from current owner evidence at sprint launch; do not infer clearance from an expected date.
CONTROLLED EXCEPTION | 4 | A-1013, A-1014, A-1015, A-1017 | Internal escalation only. | No local commitment | Named manager, legal, contact-route, or operational owner must approve a route. | Dana Morales | These accounts are physically separated from the work-now queue and carry no execution rank.
EXCLUDED / HOLD | 2 | A-1016, A-1018 | Recordkeeping or future scheduling only. | No | A-1016 remains closed; A-1018 remains held for the September agency review. | Dana Morales | No July recovery outreach.
How an account becomes customer-ready
1. The July 15 email must name the account for local execution and support the package lane.
2. The directory must show an approved contact route, and the authority matrix must support the exact offer, tier, and value.
3. The operational or billing owner supplies the exact evidence named in Required Evidence Gate; Dana marks only Case Evidence Support.
4. Release Status calculates Cleared only when all four source controls are Supported; only then may the rep make customer contact.
5. A failed control moves to Controlled Exceptions with a named owner and decision date—it is never pushed down the ranking.

## Sprint Control
Northstar July Recovery Sprint — Supervisor Work Package
One controlled package for local execution, exceptions, holds, daily checkpoints, and closeout.
Supervisor owner | Dana Morales | Approval source | Elena Whitaker — July 15 approval
Execution window | 2026-07-17 through 2026-07-24 | Daily checkpoint | 16:00 Eastern
Approved local execution | 12 | Controlled exceptions | 4
Excluded / hold | 2 | Operating rule | A planned date never overrides an uncleared evidence gate.
Supervisor operating sequence
1 | Gate | Confirm the required case evidence is attached; update only Case Evidence Support.
2 | Authorize | Confirm offer code, tier, requested value, contact route, and customer language.
3 | Assign | Release the row to the owner rep only after the first two checks pass.
4 | Checkpoint | Update outreach status, note, next step, and next-step due date by 16:00 Eastern.
5 | Escalate | Move any failed gate to the exception lane; do not improvise a customer promise.
6 | Close | On July 24 reconcile model decision, outreach result, open exceptions, and forecast-risk change.
Scope and authority guardrails
• Use only MG-15, CR-10K, RH-60, SW-PKG, or RPT-COMP where the account row passes its authority check.
• Do not promise future performance, unverified credits, new product terms, legal terms, or an uncleared operational action.
• MGR-REQ is an escalation route, not a customer offer.
• Cobalt Cloud (A-1003): local authority covers the verified CR-10K credit only; RH-60 is not eligible for Key Growth.

## Approved Work Queue
Approved Local Execution Queue
Release is formula-controlled: approval email + contact route + case evidence + offer authority must all support the exact action.
Desk Work Lane | Execution Rank | Conditional Contact Target | Account ID | Account Name | Owner Rep | Supervisor | Renewal Date | Days to Renewal | Renewal Exposure | Forecast Variance | Priority Score | Primary Issue | Case IDs | Operational Owner(s) | Expected Clearance | Required Evidence Gate | Approval Email Support | Contact Route Support | Case Evidence Support | Offer Authority Support | Release Status | Released Contact Date | Approved Offer | Authority Limit | Requested Value | Authority Check | Approved Contact | Contact Role | Preferred Channel | Timezone | Contact Restriction | Supervisor-Approved Customer Action | Customer Language Guardrail | Current Rep Commitment | Commitment Due | Outreach Status | Checkpoint Note | Next Step | Next Step Due
WORK NOW — CLEAR / PREPARE | 1 | 2026-07-20 | A-1005 | Axion Robotics | Devon Brooks | Dana Morales | 2026-08-12 |  | 410000 | -72000 | 81.7 | Audience Mismatch | CASE-7207, CASE-7208 | Product Support - Ravi Mehta, Ad Ops - Lena Ortiz | 2026-07-18 | Audience rebuild proof and package-swap feasibility confirmed by Product Support / Ad Ops. | Supported — July 15 approval | Supported — Mark Feld / Approved | Pending — evidence not yet confirmed | Supported — SW-PKG / Key Growth / $18,000 |  |  | SW-PKG | $18,000 equivalent-value package swap | 18000 | Within local authority after gate clears | Mark Feld | Final Renewal Approver | Call | Central | Approved; Needs audience proof; Unavailable July 19 | Swap misaligned audience package and reset delivery proof | Describe the equivalent-value package swap only after feasibility is documented; do not guarantee future performance. | Share audience rebuild proof | 2026-07-11 | Not started |  | Swap misaligned audience package and reset delivery proof | 2026-07-20
WORK NOW — CLEAR / PREPARE | 2 | 2026-07-17 | A-1001 | Meridian Health Partners | Maya Chen | Dana Morales | 2026-07-24 |  | 340000 | -38000 | 77.9 | Delivery Underpacing | CASE-7201, CASE-7202 | Ad Ops - Lena Ortiz, Reporting - Eli Park | 2026-07-16 | Traffic pacing confirmation and makegood inventory validation attached to CASE-7201. | Supported — July 15 approval | Supported — Dr. Lena Morris / Approved | Pending — evidence not yet confirmed | Supported — MG-15 / Key Growth / $21,000 |  |  | MG-15 | $25,000 / up to 15% of affected booked impressions | 21000 | Within local authority after gate clears | Dr. Lena Morris | Final Renewal Approver | Email then call | Eastern | Approved; Executive expects delivery plan; None | Confirm makegood inventory and delivery recovery plan | Describe the validated makegood inventory and revised delivery plan; do not promise unvalidated impressions. | Send corrected pacing plan | 2026-07-14 | Not started |  | Confirm makegood inventory and delivery recovery plan | 2026-07-17
WORK NOW — CLEAR / PREPARE | 3 | 2026-07-20 | A-1012 | Vesta Apparel Collective | Jordan Patel | Dana Morales | 2026-08-01 |  | 305000 | -52000 | 72.6 | Delivery Underpacing | CASE-7215, CASE-7216 | Ad Ops - Lena Ortiz, Billing - Nora Vale | 2026-07-18 | Makegood placement validated and invoice PO correction route documented. | Supported — July 15 approval | Supported — Marta Ruiz / Approved | Pending — evidence not yet confirmed | Supported — MG-15 / Key Growth / $24,000 |  |  | MG-15 | $25,000 / up to 15% of affected booked impressions | 24000 | Within local authority after gate clears | Marta Ruiz | Final Renewal Approver | Call | Eastern | Approved; Finance asks for PO note; Unavailable July 18 | Confirm makegood placement and invoice correction route | Describe the validated makegood placement and invoice-correction process; do not combine this with an unapproved credit. | Send makegood and PO correction note | 2026-07-12 | Not started |  | Confirm makegood placement and invoice correction route | 2026-07-20
WORK NOW — CLEAR / PREPARE | 4 | 2026-07-20 | A-1007 | Northline Insurance | Jordan Patel | Dana Morales | 2026-08-03 |  | 260000 | -40000 | 66.3 | Delivery Underpacing | CASE-7210 | Ad Ops - Lena Ortiz | 2026-07-17 | Makegood placement and revised delivery dates confirmed by Ad Ops. | Supported — July 15 approval | Supported — Samira Ahmad / Approved | Pending — evidence not yet confirmed | Supported — MG-15 / Core / $22,000 |  |  | MG-15 | $25,000 / up to 15% of affected booked impressions | 22000 | Within local authority after gate clears | Samira Ahmad | Final Renewal Approver | Email | Eastern | Approved; Legal observer on copy; None | Confirm makegood placement and revised delivery dates | Describe the validated underdelivery remedy and dates; do not guarantee future delivery. | Provide underdelivery remedy | 2026-07-14 | Not started |  | Confirm makegood placement and revised delivery dates | 2026-07-20
WORK NOW — CLEAR / PREPARE | 5 | 2026-07-17 | A-1003 | Cobalt Cloud Systems | Priya Nair | Dana Morales | 2026-08-05 |  | 295000 | -35000 | 66.1 | Billing Error | CASE-7204, CASE-7205 | Billing - Nora Vale, Sales Ops - Aaron Kim | 2026-07-16 | Verified credit memo up to $9,500 attached; any rate-hold request removed or separately escalated. | Supported — July 15 approval | Supported — Rafael Soto / Approved | Pending — evidence not yet confirmed | Supported — CR-10K / Key Growth / $9,500 |  |  | CR-10K | $10,000 verified invoice credit | 9500 | CR-10K only; RH-60 is not eligible for Key Growth | Rafael Soto | Final Renewal Approver | Call | Pacific | Approved; Wants billing proof first; Unavailable July 22 AM | Confirm verified invoice credit only; escalate any rate-hold request | Discuss only the verified invoice credit under CR-10K. Do not offer a local rate hold because Key Growth is not RH-60 eligible. | Confirm billing investigation opened | 2026-07-12 | Not started |  | Confirm verified invoice credit only; escalate any rate-hold request | 2026-07-17
WORK NOW — CLEAR / PREPARE | 6 | 2026-07-17 | A-1009 | Copper Trail Hospitality | Luis Romero | Dana Morales | 2026-07-29 |  | 190000 | -25000 | 64.1 | Creative Trafficking | CASE-7212 | Ad Ops - Lena Ortiz | 2026-07-16 | Creative approval proof and equivalent package-swap feasibility confirmed by Ad Ops. | Supported — July 15 approval | Supported — Cora Lind / Approved | Pending — evidence not yet confirmed | Supported — SW-PKG / Core / $15,000 |  |  | SW-PKG | $18,000 equivalent-value package swap | 15000 | Within local authority after gate clears | Cora Lind | Final Renewal Approver | Call | Pacific | Approved; Sensitive to launch dates; Unavailable July 20 PM | Confirm package swap and creative approval timeline | Describe the approved equivalent-value swap and confirmed timeline; do not promise launch timing before validation. | Send brand safety approval path | 2026-07-13 | Not started |  | Confirm package swap and creative approval timeline | 2026-07-17
WORK NOW — CLEAR / PREPARE | 7 | 2026-07-21 | A-1002 | Larkspur Credit Union | Jordan Patel | Dana Morales | 2026-07-31 |  | 220000 | -21000 | 58.7 | Reporting Discrepancy | CASE-7203 | Reporting - Eli Park | 2026-07-17 | Corrected reach report and customer-facing reconciliation summary attached. | Supported — July 15 approval | Supported — Tanya Wells / Approved | Pending — evidence not yet confirmed | Supported — RPT-COMP / Core / $0 |  |  | RPT-COMP | No credit; reporting reconciliation package | 0 | Within local authority after gate clears | Tanya Wells | Final Renewal Approver | Email | Central | Approved; Compliance copy required; Avoid Friday after 12:00 | Deliver reconciled reporting package and executive summary | Provide the reconciled reporting package; make no commercial or performance promise. | Provide reconciled reach report | 2026-07-17 | Not started |  | Deliver reconciled reporting package and executive summary | 2026-07-21
WORK NOW — CLEAR / PREPARE | 8 | 2026-07-17 | A-1004 | Harborview Furnishings | Luis Romero | Dana Morales | 2026-07-28 |  | 150000 | -13000 | 58 | Creative Trafficking | CASE-7206 | Ad Ops - Lena Ortiz | 2026-07-16 | Creative retagging confirmation and package-swap feasibility documented by Ad Ops. | Supported — July 15 approval | Supported — Nina Cho / Approved | Pending — evidence not yet confirmed | Supported — SW-PKG / Core / $12,000 |  |  | SW-PKG | $18,000 equivalent-value package swap | 12000 | Within local authority after gate clears | Nina Cho | Final Renewal Approver | Email | Pacific | Approved; Creative team must be copied; None | Offer equivalent package swap after trafficking confirmation | Describe the approved equivalent-value swap after trafficking confirmation; do not promise timing before validation. | Send creative retagging ETA | 2026-07-12 | Not started |  | Offer equivalent package swap after trafficking confirmation | 2026-07-17
WORK NOW — CLEAR / PREPARE | 9 | 2026-07-21 | A-1011 | Solstice Energy Co-op | Maya Chen | Dana Morales | 2026-08-09 |  | 175000 | -20000 | 55.1 | Reporting Discrepancy | CASE-7214 | Reporting - Eli Park | 2026-07-18 | Corrected lift model and customer-facing summary attached. | Supported — July 15 approval | Supported — Imani Hart / Approved | Pending — evidence not yet confirmed | Supported — RPT-COMP / Core / $0 |  |  | RPT-COMP | No credit; reporting reconciliation package | 0 | Within local authority after gate clears | Imani Hart | Final Renewal Approver | Email | Central | Approved; Procurement copied; None | Send corrected lift summary and renewal confidence note | Provide the corrected reporting package; make no commercial or performance promise. | Send corrected lift summary | 2026-07-18 | Not started |  | Send corrected lift summary and renewal confidence note | 2026-07-21
WORK NOW — CLEAR / PREPARE | 10 | 2026-07-20 | A-1006 | Greenway Kitchens | Maya Chen | Dana Morales | 2026-07-26 |  | 82000 | -5000 | 47.8 | Billing Error | CASE-7209 | Billing - Nora Vale | 2026-07-17 | Verified credit memo up to $4,800 and corrected bill date attached. | Supported — July 15 approval | Supported — Gloria Kim / Approved | Pending — evidence not yet confirmed | Supported — CR-10K / Emerging / $4,800 |  |  | CR-10K | $10,000 verified invoice credit | 4800 | Within local authority after gate clears | Gloria Kim | Final Renewal Approver | SMS then email | Eastern | Approved; Prefers concise invoice note; None | Confirm verified invoice credit and corrected bill date | Discuss only the verified invoice correction under CR-10K; do not exceed $4,800. | Send credit memo note | 2026-07-17 | Not started |  | Confirm verified invoice credit and corrected bill date | 2026-07-20
WORK NOW — CLEAR / PREPARE | 11 | 2026-07-21 | A-1008 | Veridian Charter Schools | Priya Nair | Dana Morales | 2026-08-15 |  | 110000 | -10000 | 40.8 | Reporting Discrepancy | CASE-7211 | Reporting - Eli Park | 2026-07-20 | Corrected district reach report and renewal summary attached. | Supported — July 15 approval | Supported — Julian Pierce / Approved | Pending — evidence not yet confirmed | Supported — RPT-COMP / Emerging / $0 |  |  | RPT-COMP | No credit; reporting reconciliation package | 0 | Within local authority after gate clears | Julian Pierce | Final Renewal Approver | Email | Mountain | Approved; No vendor calls before report; School board meeting July 23 | Send reconciled district reach report and renewal summary | Provide the reconciled district report; make no commercial or performance promise. | Share district reach report | 2026-07-20 | Not started |  | Send reconciled district reach report and renewal summary | 2026-07-21
WORK NOW — CLEAR / PREPARE | 12 | 2026-07-22 | A-1010 | Finch Legal Group | Devon Brooks | Dana Morales | 2026-08-20 |  | 75000 | -2000 | 34.7 | Renewal Rate Objection | CASE-7213 | Sales Ops - Aaron Kim | 2026-07-21 | 60-day CPM hold language documented with no additional credit. | Supported — July 15 approval | Supported — Evan Finch / Approved | Pending — evidence not yet confirmed | Supported — RH-60 / Emerging / $0 |  |  | RH-60 | No credit; current CPM held for 60 days | 0 | Within local authority after gate clears | Evan Finch | Final Renewal Approver | Email | Eastern | Approved; Rate hold only; Court calendar mornings | Offer 60-day rate hold without additional credit | Offer only the 60-day current-CPM hold under RH-60; do not add a credit. | Confirm 60-day rate hold | 2026-07-21 | Not started |  | Offer 60-day rate hold without additional credit | 2026-07-22

## Cleared Contact Path
Cleared-Only Dated Contact Path
This view populates only when all four source controls calculate Release Status = Cleared. Blocked, controlled, and held accounts cannot appear here.
Released Contact Date | Account ID | Account Name | Owner Rep | Approved Contact | Preferred Channel | Supervisor-Approved Customer Action | Release Status | Outreach Status

## Daily Runbook
July 17–24 Daily Runbook
Column C prepares accounts against their conditional contact targets. Only accounts appearing on Cleared Contact Path may enter column D.
Date | Supervisor Focus | Pre-contact Clearance Work | Cleared Customer Contacts Only | Exception / Hold Check | 16:00 ET Checkpoint Deliverable | Completion Status | Supervisor Note
2026-07-17 | Launch: validate evidence, authorize only cleared rows, assign rep actions. | A-1001, A-1003, A-1004, A-1009 | None until rows appear on Cleared Contact Path | A-1014 manager credit decision | Gate status, released actions, blocked items, and owner/due date. | Not started
2026-07-20 | Clear weekend operational dependencies and run highest-risk outreach. | A-1005, A-1012, A-1007, A-1006 | Use Cleared Contact Path only | A-1013 contact-route decision | Outreach result, customer response, missed gates, and updated forecast risk. | Not started
2026-07-21 | Complete reporting-package actions and evidence-only follow-up. | A-1002, A-1011, A-1008 | Use Cleared Contact Path only | A-1015 product-feed status | Reports delivered, follow-ups booked, exception changes, and forecast risk. | Not started
2026-07-22 | Complete rate-hold action and rescue any slipped approved account. | A-1010 plus slipped approved rows | Use Cleared Contact Path only | A-1015 feed-fix decision | Completed actions, rescue assignments, outstanding customer decisions. | Not started
2026-07-23 | Resolve follow-ups and prepare closeout reconciliation. | All open approved rows | Use Cleared Contact Path only | A-1017 legal route status | Open actions with owners/dates; draft decision and forecast reconciliation. | Not started
2026-07-24 | Final follow-up and sprint closeout. | A-1001 renewal checkpoint; all remaining approved rows | Use Cleared Contact Path only | All four exceptions; confirm A-1016/A-1018 remain held | Final model decision, outreach status, exceptions, and forecast-risk change. | Not started

## Controlled Exceptions
Controlled Exception Queue
Visible to the supervisor, but not releasable as local customer commitments.
Control Lane | Account ID | Account Name | Owner Rep | Supervisor | Renewal Date | Renewal Exposure | Forecast Variance | Primary Issue | Exception Reason | Escalation Owner | Decision Due | Required Route | Customer Contact Rule | Exception Status | Checkpoint Note | Next Step
CONTROLLED — NO LOCAL COMMITMENT | A-1014 | SummitBank SMB Services | Luis Romero | Dana Morales | 2026-07-30 | 360000 | -60000 | Billing Error | Requested credit is above supervisor authority | Sales manager | 2026-07-17 | Decide the $42,000 over-limit credit route; no local credit promise. | No local commitment; evidence-only contact where directory permits. | Open |  | Decide the $42,000 over-limit credit route; no local credit promise.
CONTROLLED — NO LOCAL COMMITMENT | A-1017 | Atlas BioLabs | Jordan Patel | Dana Morales | 2026-08-28 | 520000 | -110000 | Data-Use Terms | Contract terms outside local authority | Sales manager and Legal | 2026-07-24 | Draft the data-use response through the manager/legal route; no rep commitment. | No local commitment; evidence-only contact where directory permits. | Open |  | Draft the data-use response through the manager/legal route; no rep commitment.
CONTROLLED — NO LOCAL COMMITMENT | A-1015 | Mesa Tool Supply | Devon Brooks | Dana Morales | 2026-08-07 | 210000 | -38000 | Product Feed Blocker | Ad-ops blocker not cleared | Product Support / Ad Ops | 2026-07-22 | Clear the feed blocker and provide feasibility proof before any package-swap offer. | No local commitment; evidence-only contact where directory permits. | Open |  | Clear the feed blocker and provide feasibility proof before any package-swap offer.
CONTROLLED — NO LOCAL COMMITMENT | A-1013 | BrightPath Dental Alliance | Priya Nair | Dana Morales | 2026-08-17 | 165000 | -12000 | Delivery Underpacing | Decision-maker outreach permission pending | Supervisor / contact-route approval | 2026-07-20 | Obtain permission for the final approver route; operational contact may receive issue evidence only. | No local commitment; evidence-only contact where directory permits. | Open |  | Obtain permission for the final approver route; operational contact may receive issue evidence only.

## Excluded and Holds
Excluded and Hold Records
No sprint outreach or local commercial action.
Account ID | Account Name | Owner Rep | Status | Reason | Permitted Supervisor Action | Review Date | Note
A-1016 | Riverstone Fitness | Maya Chen | Excluded — closed renewal | Issue resolved and renewal signed. | Retain closure evidence only. | 2026-07-24 | No outreach.
A-1018 | Pinyon Outdoor Media Buyers | Priya Nair | Customer hold | Agency requested September consolidation review. | Preserve hold and schedule September rebrief only. | 2026-09-02 | No July outreach.

## Source Reconciliation
Account-by-Account Source Reconciliation
Reconciles the package to CRM health, opportunity exposure, ops cases, contact authority, offer authority, the watchlist, and the July 15 approval.
Account ID | Account Name | July 15 Approval Scope | Package Control Lane | Scope Match | CRM Lifecycle State | CRM Opportunity Approval | Owner Match | Renewal Date Match | Exposure Match | Requested Value Match | Watchlist Risk Rank | Watchlist Offer | Offer / Authority Check | Ops Case Count | Ops Max Severity | Ops Average Age | Ops Status and Dependencies | Contact Route | Contact Control Check | Conditional Contact Target | Initial Release State | Overall Reconciliation | Required Supervisor Disposition | Correction / Control Note
A-1001 | Meridian Health Partners | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 2 | MG-15 | Pass | Pass | Pass | Pass | CASE-7201 Waiting on Ad Ops; CASE-7202 Open ¦ CASE-7201: Traffic pacing confirmation; CASE-7202: Reach report reconciliation | Dr. Lena Morris: Approved | Pass | 2026-07-17 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Traffic pacing confirmation and makegood inventory validation attached to CASE-7201.
A-1002 | Larkspur Credit Union | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 10 | RPT-COMP | Pass | Pass | Pass | Pass | CASE-7203 Open ¦ CASE-7203: Corrected report | Tanya Wells: Approved | Pass | 2026-07-21 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Corrected reach report and customer-facing reconciliation summary attached.
A-1003 | Cobalt Cloud Systems | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 7 | CR-10K | Pass for CR-10K only; RH-60 excluded for Key Growth | Pass | Pass | Pass | CASE-7204 Resolved Pending Customer; CASE-7205 Waiting on Sales ¦ CASE-7204: Credit memo confirmation; CASE-7205: Rate hold language | Rafael Soto: Approved | Pass | 2026-07-17 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Verified credit memo up to $9,500 attached; any rate-hold request removed or separately escalated. | Watchlist action mixed CR-10K with an ineligible RH-60 rate hold. Package restricts local action to CR-10K and treats CASE-7204 as the controlling evidence date.
A-1004 | Harborview Furnishings | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 11 | SW-PKG | Pass | Pass | Pass | Pass | CASE-7206 Waiting on Ad Ops ¦ CASE-7206: Creative retagging | Nina Cho: Approved | Pass | 2026-07-17 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Creative retagging confirmation and package-swap feasibility documented by Ad Ops.
A-1005 | Axion Robotics | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 1 | SW-PKG | Pass | Pass | Pass | Pass | CASE-7207 Open; CASE-7208 Waiting on Ad Ops ¦ CASE-7207: Audience rebuild proof; CASE-7208: Pacing reset | Mark Feld: Approved | Pass | 2026-07-20 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Audience rebuild proof and package-swap feasibility confirmed by Product Support / Ad Ops.
A-1006 | Greenway Kitchens | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 13 | CR-10K | Pass | Pass | Pass | Pass | CASE-7209 Open ¦ CASE-7209: Credit memo draft | Gloria Kim: Approved | Pass | 2026-07-20 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Verified credit memo up to $4,800 and corrected bill date attached.
A-1007 | Northline Insurance | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 6 | MG-15 | Pass | Pass | Pass | Pass | CASE-7210 Waiting on Ad Ops ¦ CASE-7210: Makegood placement | Samira Ahmad: Approved | Pass | 2026-07-20 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Makegood placement and revised delivery dates confirmed by Ad Ops.
A-1008 | Veridian Charter Schools | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 15 | RPT-COMP | Pass | Pass | Pass | Pass | CASE-7211 Open ¦ CASE-7211: Corrected district report | Julian Pierce: Approved | Pass | 2026-07-21 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Corrected district reach report and renewal summary attached.
A-1009 | Copper Trail Hospitality | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 8 | SW-PKG | Pass | Pass | Pass | Pass | CASE-7212 Waiting on Ad Ops ¦ CASE-7212: Creative approval proof | Cora Lind: Approved | Pass | 2026-07-17 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Creative approval proof and equivalent package-swap feasibility confirmed by Ad Ops.
A-1010 | Finch Legal Group | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 17 | RH-60 | Pass | Pass | Pass | Pass | CASE-7213 Waiting on Sales ¦ CASE-7213: Rate hold note | Evan Finch: Approved | Pass | 2026-07-22 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | 60-day CPM hold language documented with no additional credit.
A-1011 | Solstice Energy Co-op | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 12 | RPT-COMP | Pass | Pass | Pass | Pass | CASE-7214 Open ¦ CASE-7214: Corrected lift model | Imani Hart: Approved | Pass | 2026-07-21 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Corrected lift model and customer-facing summary attached.
A-1012 | Vesta Apparel Collective | Approved local execution | WORK NOW — CLEAR / PREPARE | Pass | Approved execution | Approved execution | Pass | Pass | Pass | Pass | 4 | MG-15 | Pass | Pass | Pass | Pass | CASE-7215 Waiting on Ad Ops; CASE-7216 Open ¦ CASE-7215: Makegood placement; CASE-7216: Invoice correction | Marta Ruiz: Approved | Pass | 2026-07-20 | Pending evidence — no customer contact | RECONCILED — PENDING EVIDENCE | Makegood placement validated and invoice PO correction route documented.
A-1013 | BrightPath Dental Alliance | Controlled exception | CONTROLLED — NO LOCAL COMMITMENT | Pass | Controlled exception | Controlled exception | Pass | Pass | Pass | Pass | 14 | MG-15 | Pass offer fit; controlled by contact permission | Pass | Pass | Pass | CASE-7217 Open ¦ CASE-7217: Pacing check | Alice Go: Pending | Controlled — final approver permission pending |  | Controlled — no local commitment | RECONCILED — CONTROLLED | Obtain permission for the final approver route; operational contact may receive issue evidence only. | Offer fit alone does not clear the account; final-approver permission remains pending.
A-1014 | SummitBank SMB Services | Controlled exception | CONTROLLED — NO LOCAL COMMITMENT | Pass | Controlled exception | Controlled exception | Pass | Pass | Pass | Pass | 3 | MGR-REQ | Controlled manager route — not a local offer | Pass | Pass | Pass | CASE-7218 Resolved Pending Customer ¦ CASE-7218: Manager approval | Brent Ivers: Approved | Consistent with hold/exception lane |  | Controlled — no local commitment | RECONCILED — CONTROLLED | Decide the $42,000 over-limit credit route; no local credit promise. | The $42,000 request exceeds local authority and remains MGR-REQ.
A-1015 | Mesa Tool Supply | Controlled exception | CONTROLLED — NO LOCAL COMMITMENT | Pass | Controlled exception | Controlled exception | Pass | Pass | Pass | Pass | 9 | SW-PKG | Pass offer fit; controlled by unresolved ops blocker | Pass | Pass | Pass | CASE-7219 Waiting on Ad Ops ¦ CASE-7219: Feed fix proof | Mei Carter: Approved | Consistent with hold/exception lane |  | Controlled — no local commitment | RECONCILED — CONTROLLED | Clear the feed blocker and provide feasibility proof before any package-swap offer. | SW-PKG fits tier/value, but the product-feed blocker prevents local release.
A-1016 | Riverstone Fitness | Excluded / hold | EXCLUDED / HOLD | Pass | Excluded - closed renewal | Excluded - no action | Pass | Pass | Pass | Pass | 16 | None | Not applicable — no local offer | Pass | Pass | Pass | No open cases ¦ None | Hannah Roy: Approved | Consistent with hold/exception lane |  | Excluded / hold — no July contact | RECONCILED — EXCLUDED / HOLD | No sprint action; keep closure note
A-1017 | Atlas BioLabs | Controlled exception | CONTROLLED — NO LOCAL COMMITMENT | Pass | Controlled exception | Controlled exception | Pass | Pass | Pass | Pass | 5 | MGR-REQ | Controlled manager route — not a local offer | Pass | Pass | Pass | CASE-7221 Open; CASE-7222 Open ¦ CASE-7221: Legal review; CASE-7222: Segment report | Dr. Paolo Kent: Do not contact executive | Controlled — executive do-not-contact / manager-legal route |  | Controlled — no local commitment | RECONCILED — CONTROLLED | Draft the data-use response through the manager/legal route; no rep commitment. | Enterprise data-use terms remain with manager/legal; executive contact is prohibited.
A-1018 | Pinyon Outdoor Media Buyers | Excluded / hold | EXCLUDED / HOLD | Pass | Excluded - September review | Excluded - no action | Pass | Pass | Pass | Pass | 18 | None | Not applicable — no local offer | Pass | Pass | Pass | CASE-7223 Waiting on Customer ¦ CASE-7223: September rebrief | Morgan Price: Pending | Hold — customer requested September review |  | Excluded / hold — no July contact | RECONCILED — EXCLUDED / HOLD | Hold for September agency review | Customer-requested September hold overrides risk priority.

## Authority Reference
Local Recovery Authority — Quick Reference
Effective July 15–September 30, 2026. The source authority document remains controlling.
Offer Code | Issue Basis | Eligible Tiers | Authority Limit | Approval | Permitted Use | If Evidence Is Missing
MG-15 | Delivery Underpacing | Key Growth, Core, Emerging | $25,000 | Supervisor | Makegood inventory up to 15% of affected booked impressions after ad-ops validation. | Hold
CR-10K | Billing Error | Key Growth, Core, Emerging | $10,000 | Supervisor | Verified invoice credit up to $10,000 with billing case attached. | Hold
RH-60 | Renewal Rate Objection | Core, Emerging | No credit | Supervisor | Hold current renewal CPM for 60 days when no extra credit is promised. | Exception
SW-PKG | Creative Trafficking; Audience Mismatch; Product Feed Blocker | Key Growth, Core, Emerging | $18,000 | Supervisor | Equivalent-value package swap after operational owner confirms feasibility. | Hold
RPT-COMP | Reporting Discrepancy | Key Growth, Core, Emerging | No credit | Supervisor | Expedited reporting reconciliation package with customer-facing summary. | Hold
MGR-REQ | Over-limit or unsupported | All | No credit | Manager required | Controlled exception route for over-limit credits, legal terms, unsupported offers, or missing authority. | Manager / functional owner

## Source Control
Source Lineage and Package Corrections
Source dates are preserved so the supervisor can identify stale evidence before release.
Source | As-of / Effective Date | Use in Package | Control Note
data/revenue_ops_review/escalation_watchlist_review_2026-07-14.xlsx | Review 2026-07-14 | Risk scores, tiers, proposed actions | Global risk rank replaced by an execution-only rank plus separate exception/hold lanes.
data/crm_health/escalated_account_health_export_2026-07-13.xlsx | Export 2026-07-13 | Account, renewal, approval, forecast context | Refresh changed renewal or approval state before outreach.
data/ad_ops_cases/open_ad_ops_case_queue_2026-07-13.csv | Queue 2026-07-13; some updates through 2026-07-14 | Case owner, dependency, expected resolution | Gate clearance requires current owner evidence, not the file date alone.
data/contacts/advertiser_contact_and_authority_directory_2026-07-10.xlsx | Directory 2026-07-10 | Approved contact route and restrictions | Reconfirm any pending or restricted route.
data/rep_activity/rep_touchpoints_and_commitments_2026-04-01_to_2026-07-14.csv | Through 2026-07-14 | Commitments, due dates, next steps | Checkpoint fields in this package become the sprint record.
data/commercial_options/local_recovery_offer_authority_q3_2026.docx | Effective 2026-07-15 to 2026-09-30 | Offer codes, caps, evidence gates, escalation rules | Controlling authority source.
data/approvals/recovery_sprint_scope_approval_2026-07-15.eml | Approved 2026-07-15 | Supervisor, execution window, account scope | Controlling sprint approval source.
Package correction: A-1003 | Applied in this workbook | Local action and guardrail | Removed unsupported RH-60 language; Key Growth is not RH-60 eligible. CR-10K only unless separately approved.