Approved Operating Playbook

# Escalated Advertiser Account Recovery

# Playbook

July 2026 recovery sprint for Northstar Media Network frontline reps

# Document Control

| Field | Approved Record |
| --- | --- |
| Owner | Dana Morales, Advertising Sales Desk Supervisor |
| Approver | Elena Whitaker, Director of Regional Sales |
| Effective window | 2026-07-17 through 2026-07-24 |
| Approved scope | 12 executable accounts; 4 controlled exceptions; 2 excluded or hold records retained for lineage. |
| Source list | CRM health, ad-ops cases, order history, contacts, rep activity, local offer authority, watchlist review, and approval email. |

# Purpose

This playbook converts the approved recovery decision into repeatable rep actions, evidence checks, customer-contact rules, and exception routes. It is for frontline execution; it does not authorize reps to negotiate terms beyond the approved local authority.

# Entry Criteria

| Entry Criteria | Evidence Field | If Not Met |
| --- | --- | --- |
| Account appears in CRM export and approval email | Account ID, opportunity ID, lifecycle state | Do not schedule |
| Issue or customer request is visible | Case ID or activity ID | Hold for evidence |
| Offer is permitted by authority guide | Offer code, issue type, cap, tier | Manager exception |
| Contact route is permitted | Contact ID and outreach permission | Hold or ops-only |

# Roles and RACI

| Workstream | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Priority decision | Supervisor | Sales manager | Revenue ops | Account reps |
| Customer outreach | Account rep | Supervisor | Ad ops or billing | Manager as needed |
| Case resolution | Functional owner | Ad ops lead | Account rep | Customer contact |
| Offer compliance | Supervisor | Sales manager | Revenue ops | Account rep |
| Checkpoint reporting | Supervisor | Sales manager | All owners | Revenue ops |

# Workflow

| Step | Procedure | Responsibility | Evidence To Record |
| --- | --- | --- | --- |
| 1 | Confirm account is in approved execution or controlled exception scope. | Supervisor | Approval status and lifecycle state |
| 2 | Verify case or activity evidence and identify actual customer request. | Rep with functional owner | Case ID, activity ID, issue type, owner |
| 3 | Check offer fit against authority guide before drafting customer language. | Supervisor | Offer code, cap, issue basis, tier |
| 4 | Use only permitted contact route and respect unavailable windows. | Rep | Contact ID, role, permission, channel |
| 5 | Complete outreach or internal handoff at scheduled time. | Rep or owner | Schedule action ID and timestamp |
| 6 | Update CRM, case queue, and checkpoint summary with confirmation state. | Rep | CRM note, case status, confirmation source |
| 7 | Escalate blockers before daily 16:00 checkpoint. | Supervisor | Exception route, owner, due date |

# Account-Specific Recovery Plans

| Account | Issue | Decision Route | Offer | Owner | Due | Approved Action Or Hold |
| --- | --- | --- | --- | --- | --- | --- |
| A-1001 Meridian Health Partners | Delivery Underpacing | Dr. Lena Morris | MG-15 | Maya Chen | 2026-07-20 | Confirm makegood inventory and delivery recovery plan |
| A-1002 Larkspur Credit Union | Reporting Discrepancy | Tanya Wells | RPT-COMP | Jordan Patel | 2026-07-24 | Deliver reconciled reporting package and executive summary |
| A-1003 Cobalt Cloud Systems | Billing Error | Rafael Soto | CR-10K | Priya Nair | 2026-07-22 | Confirm verified billing credit and renewal rate hold |
| A-1004 Harborview Furnishings | Creative Trafficking | Nina Cho | SW-PKG | Luis Romero | 2026-07-24 | Offer equivalent package swap after trafficking confirmation |
| A-1005 Axion Robotics | Audience Mismatch | Mark Feld | SW-PKG | Devon Brooks | 2026-07-20 | Swap misaligned audience package and reset delivery proof |
| A-1006 Greenway Kitchens | Billing Error | Gloria Kim | CR-10K | Maya Chen | 2026-07-24 | Confirm verified invoice credit and corrected bill date |
| A-1007 Northline Insurance | Delivery Underpacing | Samira Ahmad | MG-15 | Jordan Patel | 2026-07-22 | Confirm makegood placement and revised delivery dates |
| A-1008 Veridian Charter Schools | Reporting Discrepancy | Julian Pierce | RPT-COMP | Priya Nair | 2026-07-24 | Send reconciled district reach report and renewal summary |
| A-1009 Copper Trail Hospitality | Creative Trafficking | Cora Lind | SW-PKG | Luis Romero | 2026-07-22 | Confirm package swap and creative approval timeline |
| A-1010 Finch Legal Group | Renewal Rate Objection | Evan Finch | RH-60 | Devon Brooks | 2026-07-24 | Offer 60-day rate hold without additional credit |
| A-1011 Solstice Energy Co-op | Reporting Discrepancy | Imani Hart | RPT-COMP | Maya Chen | 2026-07-24 | Send corrected lift summary and renewal confidence note |
| A-1012 Vesta Apparel Collective | Delivery Underpacing | Marta Ruiz | MG-15 | Jordan Patel | 2026-07-22 | Confirm makegood placement and invoice correction route |
| A-1013 BrightPath Dental Alliance | Delivery Underpacing | Alice Go | MG-15 | Priya Nair | Hold | Hold customer-facing offer until decision-maker route is approved |
| A-1014 SummitBank SMB Services | Billing Error | Brent Ivers | MGR-REQ | Luis Romero | Hold | Route credit request to manager; do not promise local credit |
| A-1015 Mesa Tool Supply | Product Feed Blocker | Mei Carter | SW-PKG | Devon Brooks | Hold | Wait for product feed fix before customer offer |
| A-1017 Atlas BioLabs | Data-Use Terms | Dr. Paolo Kent | MGR-REQ | Jordan Patel | Hold | Escalate to manager and legal owner; no rep commitment |

# Decision Points and Exceptions

| Decision Point | Approved Route | Exception Route |
| --- | --- | --- |
| Offer request exceeds cap | No customer commitment beyond local cap | Manager review using MGR-REQ |
| Operational blocker unresolved | Internal case handoff only | Ad ops owner clears dependency before customer offer |
| Decision maker not approved | Use permitted ops contact for evidence only | Supervisor secures permission or holds |
| Legal term requested | Rep records request | Manager/legal route; no local commitment |

# Controls and Checklists

| Checklist | Evidence Field | Owner | Complete |
| --- | --- | --- | --- |
| Pre-call readiness | Case, offer, contact, script, fallback route | Rep | Field |
| Post-call confirmation | Customer response, next step, due date | Rep | Field |
| CRM update | Stage, forecast category, task, note | Rep | Field |
| Case update | Status, owner, expected resolution | Functional owner | Field |
| Daily checkpoint | Completed, blocked, exception, forecast risk | Supervisor | Field |

# Handoff and Closeout

The supervisor closes the sprint only after approved outreach, operational handoffs, CRM notes, case updates, and manager exception routes agree with the model and schedule. Open controlled exceptions remain active until the assigned owner confirms a route or removes the account from local recovery scope.