## Read_Me
Field | Value
Execution window | 2026-07-17 through 2026-07-24
Checkpoint cadence | Daily at 16:00 Eastern
Lifecycle state | Approved executable record
Owner rule | Only approved-execution accounts receive customer-facing commitments; controlled exceptions receive internal clearance tasks.
OwnerList | ChannelList | ScheduleStatusList | DependencyStateList | ScheduleExceptionRouteList
Devon Brooks | Phone | Planned | Ready | Supervisor checkpoint
Jordan Patel | Email | Confirmed | Blocked | Reschedule before daily 16:00 checkpoint
Luis Romero | CRM task | Completed |  | Requested credit is above supervisor authority
Maya Chen | Internal | Blocked |  | Decision-maker outreach permission pending
Priya Nair |  | Rescheduled |  | Ad-ops blocker not cleared
|  | Escalated |  | Contract terms outside local authority

## Action_Register
Action ID | Account ID | Account Name | Priority Tier | Decision Status | Owner Rep | Backup Owner | Contact ID | Contact Name | Channel | Action Type | Approved Offer | Source Case ID | Dependency | Scheduled Start | Duration Min | Buffer Min | Status | Confirmation State | Contingency Route
RA-001 | A-1005 | Axion Robotics | Tier 1 | Approved execution | Devon Brooks | Luis Romero | CT-005A | Mark Feld | Phone | Customer recovery call | SW-PKG | CASE-7207 | Audience proof deck | 2026-07-17 09:00 | 45 | 30 | Planned | Not sent | Supervisor checkpoint
RA-001F | A-1005 | Axion Robotics | Tier 1 | Approved execution | Devon Brooks | Luis Romero | CT-005A | Mark Feld | CRM task | Post-contact confirmation and CRM update | SW-PKG | CASE-7207 | Customer response from first touch | 2026-07-18 11:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-002 | A-1001 | Meridian Health Partners | Tier 1 | Approved execution | Maya Chen | Devon Brooks | CT-001A | Dr. Lena Morris | Phone | Customer recovery call | MG-15 | CASE-7201 | Ad ops pacing confirmation | 2026-07-17 10:15 | 45 | 30 | Planned | Not sent | Supervisor checkpoint
RA-002F | A-1001 | Meridian Health Partners | Tier 1 | Approved execution | Maya Chen | Devon Brooks | CT-001A | Dr. Lena Morris | CRM task | Post-contact confirmation and CRM update | MG-15 | CASE-7201 | Customer response from first touch | 2026-07-18 12:15 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-003 | A-1012 | Vesta Apparel Collective | Tier 2 | Approved execution | Jordan Patel | Maya Chen | CT-012A | Marta Ruiz | Phone | Customer recovery call | MG-15 | CASE-7215 | Invoice correction owner | 2026-07-17 11:30 | 45 | 30 | Planned | Not sent | Supervisor checkpoint
RA-003F | A-1012 | Vesta Apparel Collective | Tier 2 | Approved execution | Jordan Patel | Maya Chen | CT-012A | Marta Ruiz | CRM task | Post-contact confirmation and CRM update | MG-15 | CASE-7215 | Customer response from first touch | 2026-07-18 13:30 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-004 | A-1007 | Northline Insurance | Tier 2 | Approved execution | Jordan Patel | Devon Brooks | CT-007A | Samira Ahmad | Email | Customer recovery email | MG-15 | CASE-7210 | Makegood placement | 2026-07-17 13:00 | 30 | 30 | Planned | Not sent | Supervisor checkpoint
RA-004F | A-1007 | Northline Insurance | Tier 2 | Approved execution | Jordan Patel | Devon Brooks | CT-007A | Samira Ahmad | CRM task | Post-contact confirmation and CRM update | MG-15 | CASE-7210 | Customer response from first touch | 2026-07-18 15:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-005 | A-1003 | Cobalt Cloud Systems | Tier 2 | Approved execution | Priya Nair | Jordan Patel | CT-003A | Rafael Soto | Phone | Customer recovery call | CR-10K | CASE-7204 | Credit memo draft | 2026-07-20 09:30 | 45 | 30 | Planned | Not sent | Supervisor checkpoint
RA-005F | A-1003 | Cobalt Cloud Systems | Tier 2 | Approved execution | Priya Nair | Jordan Patel | CT-003A | Rafael Soto | CRM task | Post-contact confirmation and CRM update | CR-10K | CASE-7204 | Customer response from first touch | 2026-07-21 11:30 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-006 | A-1009 | Copper Trail Hospitality | Tier 2 | Approved execution | Luis Romero | Jordan Patel | CT-009A | Cora Lind | Phone | Customer recovery call | SW-PKG | CASE-7212 | Creative approval proof | 2026-07-20 11:00 | 45 | 30 | Planned | Not sent | Supervisor checkpoint
RA-006F | A-1009 | Copper Trail Hospitality | Tier 2 | Approved execution | Luis Romero | Jordan Patel | CT-009A | Cora Lind | CRM task | Post-contact confirmation and CRM update | SW-PKG | CASE-7212 | Customer response from first touch | 2026-07-21 13:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-007 | A-1002 | Larkspur Credit Union | Tier 3 | Approved execution | Jordan Patel | Maya Chen | CT-002A | Tanya Wells | Email | Reporting package send | RPT-COMP | CASE-7203 | Corrected reach report | 2026-07-20 13:30 | 30 | 30 | Planned | Not sent | Supervisor checkpoint
RA-007F | A-1002 | Larkspur Credit Union | Tier 3 | Approved execution | Jordan Patel | Maya Chen | CT-002A | Tanya Wells | CRM task | Post-contact confirmation and CRM update | RPT-COMP | CASE-7203 | Customer response from first touch | 2026-07-21 15:30 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-008 | A-1004 | Harborview Furnishings | Tier 3 | Approved execution | Luis Romero | Priya Nair | CT-004A | Nina Cho | Email | Package swap confirmation | SW-PKG | CASE-7206 | Retagging ETA | 2026-07-21 09:30 | 35 | 30 | Planned | Not sent | Supervisor checkpoint
RA-008F | A-1004 | Harborview Furnishings | Tier 3 | Approved execution | Luis Romero | Priya Nair | CT-004A | Nina Cho | CRM task | Post-contact confirmation and CRM update | SW-PKG | CASE-7206 | Customer response from first touch | 2026-07-22 11:30 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-009 | A-1011 | Solstice Energy Co-op | Tier 3 | Approved execution | Maya Chen | Jordan Patel | CT-011A | Imani Hart | Email | Reporting package send | RPT-COMP | CASE-7214 | Corrected lift model | 2026-07-21 11:00 | 30 | 30 | Planned | Not sent | Supervisor checkpoint
RA-009F | A-1011 | Solstice Energy Co-op | Tier 3 | Approved execution | Maya Chen | Jordan Patel | CT-011A | Imani Hart | CRM task | Post-contact confirmation and CRM update | RPT-COMP | CASE-7214 | Customer response from first touch | 2026-07-22 13:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-010 | A-1008 | Veridian Charter Schools | Tier 3 | Approved execution | Priya Nair | Maya Chen | CT-008A | Julian Pierce | Email | Reporting package send | RPT-COMP | CASE-7211 | District reach report | 2026-07-22 10:00 | 30 | 30 | Planned | Not sent | Supervisor checkpoint
RA-010F | A-1008 | Veridian Charter Schools | Tier 3 | Approved execution | Priya Nair | Maya Chen | CT-008A | Julian Pierce | CRM task | Post-contact confirmation and CRM update | RPT-COMP | CASE-7211 | Customer response from first touch | 2026-07-23 12:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-011 | A-1006 | Greenway Kitchens | Tier 3 | Approved execution | Maya Chen | Priya Nair | CT-006A | Gloria Kim | Email | Credit confirmation | CR-10K | CASE-7209 | Billing credit memo | 2026-07-22 13:00 | 25 | 20 | Planned | Not sent | Supervisor checkpoint
RA-011F | A-1006 | Greenway Kitchens | Tier 3 | Approved execution | Maya Chen | Priya Nair | CT-006A | Gloria Kim | CRM task | Post-contact confirmation and CRM update | CR-10K | CASE-7209 | Customer response from first touch | 2026-07-23 15:00 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-012 | A-1010 | Finch Legal Group | Tier 3 | Approved execution | Devon Brooks | Luis Romero | CT-010A | Evan Finch | Email | Rate hold confirmation | RH-60 | CASE-7213 | Rate hold language | 2026-07-23 10:30 | 25 | 20 | Planned | Not sent | Supervisor checkpoint
RA-012F | A-1010 | Finch Legal Group | Tier 3 | Approved execution | Devon Brooks | Luis Romero | CT-010A | Evan Finch | CRM task | Post-contact confirmation and CRM update | RH-60 | CASE-7213 | Customer response from first touch | 2026-07-24 12:30 | 20 | 15 | Planned | Pending first touch | Reschedule before daily 16:00 checkpoint
RA-013 | A-1014 | SummitBank SMB Services | Controlled exception/hold | Controlled exception | Luis Romero | Jordan Patel |  | Internal owner | Internal | Manager exception review | MGR-REQ | CASE-7218 | Over-limit credit approval | 2026-07-17 15:00 | 30 | 15 | Blocked | Internal hold | Requested credit is above supervisor authority
RA-014 | A-1013 | BrightPath Dental Alliance | Controlled exception/hold | Controlled exception | Priya Nair | Devon Brooks |  | Internal owner | Internal | Contact-route clearance | MG-15 | CASE-7217 | Decision-maker permission | 2026-07-20 15:00 | 30 | 15 | Blocked | Internal hold | Decision-maker outreach permission pending
RA-015 | A-1015 | Mesa Tool Supply | Controlled exception/hold | Controlled exception | Devon Brooks | Luis Romero |  | Internal owner | Internal | Ad-ops blocker clearance | SW-PKG | CASE-7219 | Feed proof | 2026-07-21 15:00 | 30 | 15 | Blocked | Internal hold | Ad-ops blocker not cleared
RA-016 | A-1017 | Atlas BioLabs | Controlled exception/hold | Controlled exception | Jordan Patel | Maya Chen |  | Internal owner | Internal | Manager/legal exception review | MGR-REQ | CASE-7221 | Legal owner response | 2026-07-22 15:00 | 45 | 15 | Blocked | Internal hold | Contract terms outside local authority

## Schedule
Action ID | Account ID | Owner Rep | Scheduled Start | Duration Min | Buffer Min | Calculated End | Day | Status | Dependency
RA-001 | A-1005 | Devon Brooks | 2026-07-17 09:00 | 45 | 30 |  |  | Planned | Audience proof deck
RA-001F | A-1005 | Devon Brooks | 2026-07-18 11:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-002 | A-1001 | Maya Chen | 2026-07-17 10:15 | 45 | 30 |  |  | Planned | Ad ops pacing confirmation
RA-002F | A-1001 | Maya Chen | 2026-07-18 12:15 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-003 | A-1012 | Jordan Patel | 2026-07-17 11:30 | 45 | 30 |  |  | Planned | Invoice correction owner
RA-003F | A-1012 | Jordan Patel | 2026-07-18 13:30 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-004 | A-1007 | Jordan Patel | 2026-07-17 13:00 | 30 | 30 |  |  | Planned | Makegood placement
RA-004F | A-1007 | Jordan Patel | 2026-07-18 15:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-005 | A-1003 | Priya Nair | 2026-07-20 09:30 | 45 | 30 |  |  | Planned | Credit memo draft
RA-005F | A-1003 | Priya Nair | 2026-07-21 11:30 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-006 | A-1009 | Luis Romero | 2026-07-20 11:00 | 45 | 30 |  |  | Planned | Creative approval proof
RA-006F | A-1009 | Luis Romero | 2026-07-21 13:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-007 | A-1002 | Jordan Patel | 2026-07-20 13:30 | 30 | 30 |  |  | Planned | Corrected reach report
RA-007F | A-1002 | Jordan Patel | 2026-07-21 15:30 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-008 | A-1004 | Luis Romero | 2026-07-21 09:30 | 35 | 30 |  |  | Planned | Retagging ETA
RA-008F | A-1004 | Luis Romero | 2026-07-22 11:30 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-009 | A-1011 | Maya Chen | 2026-07-21 11:00 | 30 | 30 |  |  | Planned | Corrected lift model
RA-009F | A-1011 | Maya Chen | 2026-07-22 13:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-010 | A-1008 | Priya Nair | 2026-07-22 10:00 | 30 | 30 |  |  | Planned | District reach report
RA-010F | A-1008 | Priya Nair | 2026-07-23 12:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-011 | A-1006 | Maya Chen | 2026-07-22 13:00 | 25 | 20 |  |  | Planned | Billing credit memo
RA-011F | A-1006 | Maya Chen | 2026-07-23 15:00 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-012 | A-1010 | Devon Brooks | 2026-07-23 10:30 | 25 | 20 |  |  | Planned | Rate hold language
RA-012F | A-1010 | Devon Brooks | 2026-07-24 12:30 | 20 | 15 |  |  | Planned | Customer response from first touch
RA-013 | A-1014 | Luis Romero | 2026-07-17 15:00 | 30 | 15 |  |  | Blocked | Over-limit credit approval
RA-014 | A-1013 | Priya Nair | 2026-07-20 15:00 | 30 | 15 |  |  | Blocked | Decision-maker permission
RA-015 | A-1015 | Devon Brooks | 2026-07-21 15:00 | 30 | 15 |  |  | Blocked | Feed proof
RA-016 | A-1017 | Jordan Patel | 2026-07-22 15:00 | 45 | 15 |  |  | Blocked | Legal owner response

## Dependencies
Action ID | Account ID | Dependency Type | Dependency Detail | Readiness State | Owner | Exception Route
RA-001 | A-1005 | Case | Audience proof deck | Ready | Devon Brooks | Supervisor checkpoint
RA-001F | A-1005 | Offer | Customer response from first touch | Ready | Devon Brooks | Reschedule before daily 16:00 checkpoint
RA-002 | A-1001 | Case | Ad ops pacing confirmation | Ready | Maya Chen | Supervisor checkpoint
RA-002F | A-1001 | Offer | Customer response from first touch | Ready | Maya Chen | Reschedule before daily 16:00 checkpoint
RA-003 | A-1012 | Offer | Invoice correction owner | Ready | Jordan Patel | Supervisor checkpoint
RA-003F | A-1012 | Offer | Customer response from first touch | Ready | Jordan Patel | Reschedule before daily 16:00 checkpoint
RA-004 | A-1007 | Offer | Makegood placement | Ready | Jordan Patel | Supervisor checkpoint
RA-004F | A-1007 | Offer | Customer response from first touch | Ready | Jordan Patel | Reschedule before daily 16:00 checkpoint
RA-005 | A-1003 | Offer | Credit memo draft | Ready | Priya Nair | Supervisor checkpoint
RA-005F | A-1003 | Offer | Customer response from first touch | Ready | Priya Nair | Reschedule before daily 16:00 checkpoint
RA-006 | A-1009 | Case | Creative approval proof | Ready | Luis Romero | Supervisor checkpoint
RA-006F | A-1009 | Offer | Customer response from first touch | Ready | Luis Romero | Reschedule before daily 16:00 checkpoint
RA-007 | A-1002 | Offer | Corrected reach report | Ready | Jordan Patel | Supervisor checkpoint
RA-007F | A-1002 | Offer | Customer response from first touch | Ready | Jordan Patel | Reschedule before daily 16:00 checkpoint
RA-008 | A-1004 | Offer | Retagging ETA | Ready | Luis Romero | Supervisor checkpoint
RA-008F | A-1004 | Offer | Customer response from first touch | Ready | Luis Romero | Reschedule before daily 16:00 checkpoint
RA-009 | A-1011 | Offer | Corrected lift model | Ready | Maya Chen | Supervisor checkpoint
RA-009F | A-1011 | Offer | Customer response from first touch | Ready | Maya Chen | Reschedule before daily 16:00 checkpoint
RA-010 | A-1008 | Offer | District reach report | Ready | Priya Nair | Supervisor checkpoint
RA-010F | A-1008 | Offer | Customer response from first touch | Ready | Priya Nair | Reschedule before daily 16:00 checkpoint
RA-011 | A-1006 | Offer | Billing credit memo | Ready | Maya Chen | Supervisor checkpoint
RA-011F | A-1006 | Offer | Customer response from first touch | Ready | Maya Chen | Reschedule before daily 16:00 checkpoint
RA-012 | A-1010 | Offer | Rate hold language | Ready | Devon Brooks | Supervisor checkpoint
RA-012F | A-1010 | Offer | Customer response from first touch | Ready | Devon Brooks | Reschedule before daily 16:00 checkpoint
RA-013 | A-1014 | Contact | Over-limit credit approval | Blocked | Luis Romero | Requested credit is above supervisor authority
RA-014 | A-1013 | Contact | Decision-maker permission | Blocked | Priya Nair | Decision-maker outreach permission pending
RA-015 | A-1015 | Case | Feed proof | Blocked | Devon Brooks | Ad-ops blocker not cleared
RA-016 | A-1017 | Contact | Legal owner response | Blocked | Jordan Patel | Contract terms outside local authority

## Capacity
Owner Rep | Scheduled Tasks | Scheduled Minutes | Available Minutes | Buffer Minutes | Over Capacity
Devon Brooks |  |  | 480
Jordan Patel |  |  | 480
Luis Romero |  |  | 480
Maya Chen |  |  | 480
Priya Nair |  |  | 480

## Status_History
Checkpoint Date | Planned | Confirmed | Completed | Blocked | Rescheduled | Escalated
2026-07-17 | 24 | 0 | 0 | 4 | 0 | 0
2026-07-20 | 18 | 5 | 4 | 4 | 1 | 1
2026-07-21 | 14 | 9 | 8 | 3 | 1 | 1
2026-07-22 | 10 | 12 | 11 | 2 | 1 | 1
2026-07-24 | 4 | 16 | 16 | 1 | 0 | 1

## Checkpoint Summary
Metric | Value
Approved execution actions
Controlled exception actions
Blocked actions
Total scheduled minutes
Earliest Tier 1 start

## Schedule_Chart_Data
Date | Tier 1 | Tier 2 | Tier 3 | Controlled exception/hold
2026-07-17 | 2 | 2 | 0 | 1
2026-07-18 | 2 | 2 | 0 | 0
2026-07-20 | 0 | 2 | 1 | 1
2026-07-21 | 0 | 2 | 3 | 1
2026-07-22 | 0 | 0 | 4 | 1
2026-07-23 | 0 | 0 | 3 | 0
2026-07-24 | 0 | 0 | 1 | 0
Owner | Scheduled tasks | Duration hours | Available slots |  |  | Dependency Type | Ready | Blocked
Devon Brooks | 5 | 2.3 | 8 |  |  | Approval | 0 | 0
Jordan Patel | 7 | 3.5 | 8 |  |  | Case | 3 | 1
Luis Romero | 5 | 2.5 | 8 |  |  | Contact | 0 | 3
Maya Chen | 6 | 2.7 | 8 |  |  | Offer | 21 | 0
Priya Nair | 5 | 2.4 | 8
Status | Actions |  |  | Date | Scheduled hours | Available hours | Buffer hours
Planned | 24 |  |  | 2026-07-17 | 3.25 | 7.5
Confirmed | 0 |  |  | 2026-07-18 | 1.33 | 7.5
Completed | 0 |  |  | 2026-07-20 | 2.5 | 7.5
Blocked | 4 |  |  | 2026-07-21 | 2.58 | 7.5
Rescheduled | 0 |  |  | 2026-07-22 | 2.33 | 7.5
Escalated | 0 |  |  | 2026-07-23 | 1.08 | 7.5
|  |  |  | 2026-07-24 | 0.33 | 7.5