Manager Risk Brief

# Approved Recovery Sprint Risk Brief

Escalated advertiser renewal portfolio, July 2026

# Decision Header

| Field | Approved Decision Record |
| --- | --- |
| Decision | Execute a value-and-risk prioritized recovery sprint for locally approved escalated advertiser accounts. |
| Approver | Elena Whitaker, Director of Regional Sales, approved 2026-07-15. |
| Scope | 18-account portfolio; 12 approved for local execution; 4 controlled exceptions; 2 excluded or hold records. |
| Execution window | 2026-07-17 through 2026-07-24 with daily 16:00 Eastern checkpoints. |
| Lifecycle state | Approved executable record; unsupported items stay controlled exceptions. |

# Executive Summary

The recommended sprint prioritizes the locally executable accounts with the strongest combination of renewal exposure, operational recovery risk, urgent renewal timing, and ready customer contact paths. The package protects local authority by routing over-limit, legal, contact-permission, and unresolved blocker issues as controlled exceptions rather than implied commitments.

The approved local sprint covers $2,612,000 of renewal exposure; the full 18-account portfolio carries $4,064,000 in exposure and a current Q3 forecast variance of ($557,000) versus the 2025 baseline.

# Portfolio Evidence

| Metric | Value | Evidence Basis |
| --- | --- | --- |
| Total portfolio exposure | $4,064,000 | 18 CRM accounts |
| Approved executable exposure | $2,612,000 | 12 approved execution accounts |
| Controlled exception exposure | $1,255,000 | 4 accounts |
| Q3 forecast variance | ($557,000) | Current forecast minus 2025 Q3 baseline |

## Portfolio Matrix

The portfolio matrix plots renewal exposure against operational recovery risk so the manager can see why the sprint focuses on high-value, high-risk accounts while preserving manager-route exceptions.

Figure 1. Renewal exposure and operational recovery risk by approved priority route.

Source: account_prioritization_model.xlsx Dashboard, using CRM, order, case, contact, activity, offer, and approval evidence.

# Alternatives Considered

| Option | Benefit | Risk | Decision |
| --- | --- | --- | --- |
| Value-and-risk priority sprint | Focuses 12 executable accounts with $2,612,000 exposure while preserving controls. | Requires tight owner capacity checks. | Approved |
| Equal coverage by rep | Simple to assign and explain. | Delays high-risk accounts such as Axion Robotics and Meridian Health Partners. | Rejected |
| Manager-only escalation queue | Reduces local commercial risk. | Creates avoidable delay for accounts already within authority. | Rejected |

# Approved Actions

| Owner | Account | Approved Action | Due | Dependency |
| --- | --- | --- | --- | --- |
| Devon Brooks | A-1005 Axion Robotics | Swap misaligned audience package and reset delivery proof | 2026-07-20 | Audience Mismatch |
| Maya Chen | A-1001 Meridian Health Partners | Confirm makegood inventory and delivery recovery plan | 2026-07-20 | Delivery Underpacing |
| Jordan Patel | A-1012 Vesta Apparel Collective | Confirm makegood placement and invoice correction route | 2026-07-22 | Delivery Underpacing |
| Jordan Patel | A-1007 Northline Insurance | Confirm makegood placement and revised delivery dates | 2026-07-22 | Delivery Underpacing |
| Priya Nair | A-1003 Cobalt Cloud Systems | Confirm verified billing credit and renewal rate hold | 2026-07-22 | Billing Error |
| Luis Romero | A-1009 Copper Trail Hospitality | Confirm package swap and creative approval timeline | 2026-07-22 | Creative Trafficking |

# Open Controlled Exceptions

| Account | Exposure | Reason | Route |
| --- | --- | --- | --- |
| A-1013 BrightPath Dental Alliance | $165,000 | Decision-maker outreach permission pending | Hold customer-facing offer until decision-maker route is approved |
| A-1014 SummitBank SMB Services | $360,000 | Requested credit is above supervisor authority | Route credit request to manager; do not promise local credit |
| A-1015 Mesa Tool Supply | $210,000 | Ad-ops blocker not cleared | Wait for product feed fix before customer offer |
| A-1017 Atlas BioLabs | $520,000 | Contract terms outside local authority | Escalate to manager and legal owner; no rep commitment |

# Risk Register

| Risk | Control | Owner | Checkpoint |
| --- | --- | --- | --- |
| Commercial overreach | Offer compliance check and MGR-REQ route for over-limit items. | Supervisor | Daily 16:00 |
| Customer contact without permission | Use contact directory; hold or ops-only route when permission is absent. | Rep | Before outreach |
| Ad-ops blocker delays | Schedule dependency clearance before customer offer confirmation. | Functional owner | Within sprint |
| Rep capacity pressure | Capacity sheet checks owner workload and backup owner need. | Supervisor | Daily 16:00 |
| Forecast variance persists | Brief and model reconcile variance by segment and exception status. | Revenue ops | Closeout |

# Approval and Closeout Controls

Execution may proceed only for the approved local scope. The supervisor will report completed outreach, unresolved dependencies, manager exceptions, and forecast movement at each checkpoint and at final closeout. A controlled exception can move to execution only after the approval evidence, offer authority, contact route, and operational blocker state agree.